## Bid Form
Terraces North at Turnberry - Pool Improvements and Restoration Services
Client Information: |  |  | Engineer Information: |  | Bidder Information:
Address: | 1505 N Riverside Dr Pompano Beach, FL 33062 |  |  | Marcon Forensics | Company:
Client: | Intracoastal Tower Condominium Association |  |  | EOR: Charles S Long | Bidder Name:
P.O.C: | Dave Barbour |  |  | P.O.C.: Jholyn Gutierrez | Title:
Phone: | (954) 931-8886 |  |  | Phone: 561.260.4432 | Office Phone/Cell:
Email: | dave@redoaksshutter.com |  |  | Email: jholyn@marconforensics.com | Email:
Scope of Work:
Work includes the complete remodel of the pool area, including construction of a new concrete pool shell, new stairs, and a fully updated saltwater aquatic system in accordance with the design and code requirements. Scope encompasses all associated aquatic elements, including installation of a collector tank, structural modifications, and waterproofing. Work also includes updates to the pool equipment room to meet design and code requirements, concrete restorations at selected areas, pool deck waterproofing, wall coatings, painting, joint sealing, and potential additions to planters all as shown in the aquatic design documents and structural design drawings.
Pool(s), Pool(s) Appurtenances, and Aquatic Based Requirements Base Bid:
ITEM # | AREA | DESCRIPTION |  |  | QTY | QTY TYPE | UNIT COST | BID AMOUNT
1 | Mobilization & General Conditions | General Field Condition Requirements (Including but not limited to Project Manager, Superintendent, Project Coordinator, Quality Control, Community Notifications, Onsite Office/Storage Facilities and Logistics including Lifts, Scaffolding, Dump Fees, Obtaining permits, travel expenses, etc.), All insurances, Freight, Taxes, Contractors OH & P. |  |  | 1 | Lump Sum | 0 | 0
2 | Top of Slab Concrete Repairs | In conjunction with other repairs, restore damaged concrete as specified in the contract documents. Refer to Marcon Repair Drawings dated 10/15/2024. |  |  | 20 | SqFt | 0 | 0
3 | Vertical/Wall Concrete Wall (Pool Equipment Room) | In conjunction with other repairs, restore damaged concrete as specified in the contract documents. Work to include wall penetrations necessary for new ventilation exhaust fan, electircal, piping etc. Refer to Broward Engineering - Pool Remodel drawings dated 07/30/2025, Marcon Pool Project concrete drawings dated 07/21/2025 & Marcon Repair Drawings dated 10/15/2024. |  |  | 50 | Sqft | 0 | 0
4 | Overhead Concrete Slab Repair | In conjunction with other repairs, restore damaged concrete as specified in the contract documents. |  |  | 10 | SqFt | 0 | 0
5 | Concrete Restoration (Full Pool Shell) | Work includes restoring concrete and reinforcement throughout the full pool shell, including all items and conditions shown in the Marcon Pool Project concrete drawings dated 07/21/2025, in conjunction with Broward Engineering - Pool Remodel drawings dated 07/30/2025, and other repairs specified in the contract documents. Contractor to verify all measurements onsite. Concrete mix design shall be submitted to the Engineer of Record (EOR) for approval. New Reinforcement for pool floor is pending on Coastal’s response. |  |  | 1 | Lump Sum | 0 | 0
7 | Concrete Stairs with Structural Foam | Work includes constructing concrete stairs according to Marcon's - Pool Project drawings dated 07/21/2025. Complete with reinforcement and concrete placement as specified in the contract documents and project drawings. Contractor to verify all dimensions and conditions onsite. Concrete mix design and structural foam shall be submitted to the Engineer of Record (EOR) for approval. |  |  | 1 | Lump Sum | 0 | 0
8 | Partial Concrete Beam Repair | In conjuction with other repairs, restore damaged concrete as specified in the contract documents. Refer to Marcon Repair Drawings dated 10/15/2024 & Marcon - Pool Project details dated 07/21/2025. |  |  | 30 | CF | 0 | 0
9 | Partial Concrete Column Repair | In conjuction with other repairs, restore damaged concrete as specified in the contract documents. To include concrete Marcon Repair Drawings dated 10/15/2024 & Marcon - Pool Project details dated 07/21/2025 for additional details. |  |  | 10 | CF | 0 | 0
10 | Concrete Girder Repair | In conjuction with other repairs, restore damaged concrete as specified in the contract documents. To include concrete seats. Marcon Repair Drawings dated 10/15/2024 & Marcon - Pool Project details dated 07/21/2025 for additional details. |  |  | 20 | CF | 0 | 0
11 | Partial Joist Repair | Restore damaged concrete and install new concrete seats as required, in conjunction with other concrete work and in accordance with the contract documents |  |  | 25 | SqFt | 0
11 | CMU Joint Repair | In conjunction with other repairs, restore damaged joints between CMU block. Refer to Marcon Repair Drawings dated 10/15/2024. |  |  | 10 | Linear Feet | 0 | 0
12 | Epoxy Injection | In conjunction with other repairs, restore damaged concrete as specified in the contract documents.Work to include the removal, surface prep and replacement of epoxy. Refer to Marcon Repair Drawings dated 10/15/2024. |  |  | 20 | Linear Feet | 0 | 0
13 | Control Joints on Pool Deck | In conjunction with other repairs, reseal existing 1-inch wide control joints on the pool deck using Sika Sikaflex® SL 1 self-leveling polyurethane sealant. Work to include cleaning and preparation of joints, installation of backer rod as required, and application of sealant to achieve a smooth, flush finish as specified in the contract documents. |  |  | 350 | Linear Feet | 0 | 0
14 | Garage DSM Aluminum Cover Plates Sealing | Work to include the application of ½” wide bead of Sikaflex 2C 1” inboard of the edge of the plate on both sides prior to installing the aluminium plate. (plates already obtained by client). Expansion joint is approx. 140 LF, contractor to field verify. |  |  | 1 | Lump Sum | 0 | 0
15 | Planters Stucco Repair | In conjunction with other repairs, restore damaged/apply new stucco for all six existing planter walls. Priming and painting to be included in the cost. |  |  | 1 | Lump Sum | 0 | 0
16 | Collector Tank(s) Slab Openings & Supports | Work includes removal and disposal of section of the pool deck slab, concrete repairs at the openings, installation of collector tank supports per contract drawings.Refer to Broward Engineering - Pool Remodel drawings dated 07/30/2025 for location of tank/opening, Marcon Pool & Garage Repair Project drawings dated 08/20/2025, and contract documents for additional information. |  |  | 1 | Lump Sum | 0 | 0
17 | Collector Tank Area Waterproofing | Work includes substrate preparation and installation of the new waterproofing as stated on the contract drawings. |  |  | 1 | Lump Sum | 0 | 0
18 | Collector Tank Area (2nd Garage Level) Protection | Work includes installation of chain link fence with operable gate (estimated 40 LF, contractor to verify) and parking bollards for vehicular protection of the equipment. Refer to Broward Engineering - Pool Remodel drawings dated 07/30/2025. |  |  | 1 | Lump Sum | 0 | 0
19 | Pool Deck Waterproofing | Work includes substrate preparation (if any), removal and replacement of stucco as necessary for flashing, and installation of the new pool deck waterproofing on the exterior side of the new planter walls to tie into pool deck waterproofing. New pool deck waterproofing shall include Sikalastic 710 Base, Sikalastic 735 AL membrane layers, and Sikalastic FlexCoat ATC topcoat. To include all flashing for gazebos (flashing detail to be provided by Sika). Contractor is responsible for verifying all measurements onsite. This work is already accounted for in the Tower bid; however, the Sikalastic FlexCoat ATC topcoat needs to be separately priced for mateiral and installation. |  |  | 1 | Lump Sum | 0 | 0
20 | Waterproofing & Painting of Pool Equipment Room | Work includes temporary removal and replacement of any/all items and equipment as required for the application of the waterproofing system. Work includes substrate preparation and installation of the Sikagard-664 waterproofing system in-system as stated on the contract drawings and specifications. Estimated 144 SF with 6" turn-up at walls; contractor is responsible for verifying all measurements onsite. Walls/ceiling to be pressure wahsed, primed and painted with an approved sealer/primer. |  |  | 1 | Lump Sum | 0 | 0
21 | Waterstop Installation | Prepare and install new waterstop at the pool shell floor-to-wall transition to prevent cold joints. Work includes surface preparation, placement, and installation in accordance with the contract drawings and manufacturer’s installation requirements. Approx. 108 LF around pool perimeter, contractor to field verify. Contractor shall use Sika Waterbar – FB125 or approved equal, with submittal required for EOR review and approval. |  |  | 108 | LF | 0 | 0
22 | Aquatic Equipment & Appurtenances | Contractor shall install all equipment and appurtenances in accordance with Aquatic Engineering Plans for a turnkey pool installation per DOH and FBC requirements. Equipment shall include at a minimum: pool recirculation pump, cartidge filter, collector tank, flowmeter, heat pump, thermometer,pressure gauge, ORP controller, CL feeder, Acid feeder, CL container, Acid container, Chem test kit, Ring Buoy, Shepherd's hook, main drain cover & sump, handrail, ladder, equalizer cover & sump, anchor, escutcheon, skimmer, skimmer lid, new exhaust fan, new pool light, new exhaust fan, new depth marker, waterline tile, tile contrast slope break, nonslip bullnose cap tile, safety line with floats, and pool rule sign. Refer to Broward Engineering - Pool Remodel drawings dated 07/30/2025 for manufacuer specifications and quantities. All aquatic requiremnts (Includes but is not limited to piping hydraulic, pool equipment room, equipotential bonding, electrical, chemcial) requirements shall be included. |  |  | 1 | Lump Sum | 0 | 0
22.1 | Waterproofing Replacement Inside the Swimming Pool | Work includes substrate preparation. Installation of the new waterproofing as stated on the contract drawings. Work includes placement of finishes, exposed aggregate slip proof over WP (Diamond Brite Cool Blue aggregate finish material or approved equal) for the swimming pool after the waterproofing application is completed. (To be included within line item 22). |  |  | 1 | Lump Sum | Include in Line Item 22.0
22.2 | Tile/Pre-Cast Coping & Ancillary Finishes at Swimming Pool | Cost shall include the labor and installation of materials for the waterline, sub-waterline, and step marker tile. Install to TCNA Standards. *Tile/coping cost not included. Owner to coordinate with Designer for selection. (To be included within line item 22). |  |  | 175 | Lump Sum | Include in Line Item 22.0
22.3 | Swimming Pool Piping & Appurtenances Installation | Work includes removal and installation of new pool piping and accessories. (Includes but is not limited to, piping, gutter drain(s), return fittings/rings, and floor inlets as noted in the project documents.) (To be included within line item 22). |  |  | 1 | Lump Sum | Include in Line Item 22.0
22.4 | Equipotential Bonding | Verify equipotential bonding loop and provide certification by a licensed Electrical Engineer. (To be included within line item 22). |  |  | 1 | Each | Include in Line Item 22.0
22.5 | Electrical Panel Installation | Install new Siemens, GE, NEMA 4X Electrical Plan per Engineering Plan set. Refer to Broward Engineering - Pool Remodel drawings dated 07/30/2025. (To be included within line item 22). |  |  | 1 | Each | Include in Line Item 22.0
22.6 | Equipment Room Ventilation | Install new ventialtion system per Engineering Plan set. Refer to Broward Engineering - Pool Remodel drawings dated 07/30/2025. (To be included within line item 22). |  |  | 1 | Each | Include in Line Item 22.0
23 | Water heater Installation at Shower Area | Furnish and install Instant-Flow® Micro Mix® Tankless Water Heater or approved equal with built-in mixing valve at shower area, powered from pool panel (240V). Include all labor, materials, piping and electrical connections, mounting, testing, and compliance with manufacturer instructions and local codes. |  |  | 1 | Lump Sum | 0 | 0
24 | Reinstall/Paint Door at Pool Equipment Room | Work includes reinstallment of entry door at the pool equipment room with existing in accordance with the project documents. Prep, priming and painting to be included within cost. |  |  | 1 | Lump Sum | 0 | 0
25 | Pool Deck/Garage 2nd Floor Painting Preparation | Surface preparation in accordance with manufacturer requirments including but not limited to, pressure washing, removal/replacement of cracked and worn sealants and caulking on pool deck perimeter walls. To include light pressure washing for second floor garage and surface preparation. |  |  | 1 | Lump Sum | 0 | 0
26 | Pool Deck/Garage 2nd Floor Painting Application | Interior perimeter walls and 2nd level garage walls/ceiling to be painted with an approved sealer/primer. Surface prep to be included within price. Application in accordance with the provided specifications and meet or exceed the warranty requirments. Application shall be in accordance with the manufacturer requirements. The paint color is to be determined by ownership prior to application. Shuffleboard court surface prep, priming and painting to be included within cost. |  |  | 1 | Lump Sum | 0 | 0
27 | Shoring Allowance | Allowance shall include estimated costs for shoring design, delivery, installation, inspection, rental fees, equipment removal, and return services. Allowance is intended to reduce future change orders, delays for approval, and to provide an understanding that additional funds may be required for repairs. |  |  | 1 | Lump Sum | 0 | 0
28 | Permit Fees | At Cost. |  |  | 1 | Lump Sum | 0 | 0
29 | Payment and Performance Bond | Provide Cost or Percentage |  |  | 1 | Lump Sum | 0 | 0
Note: All activities mentioned herein include all required materials and required tests unless otherwise noted. See drawings for the repair schedule and general project scope of work. All quantities presented are to be used as a budgetary estimate. Contractor shall field verify quantities and obtain EOR review & approval for large discrepancies. The basis for Unit Cost repairs shall be billed at the base unit per repair location (rounded up to the nearest square foot, linear foot, cubic foot) unless otherwise agreed upon by Owner.
TOTAL COST (BASE BID): | [5 empty] | 0
ESTIMATED PROJECT DURATION (BASE BID):
Add/Alternatives
A-1 | Planter Waterproofing | Work includes substrate preparation and installation of the new waterproofing as stated on the contract drawings. |  |  | 1 | Each | 0 | 0
A-2 | New Planter Wall Modification | Work includes the installation of new planter walls per landscaping drawings. |  |  | 1 | Each | 0 | 0
A-3 | Free-standing Showerhead Replacement | Furnish and install AMA ¦ Marte MA7000 Outdoor Foot Washer Column or approved equal at shower area. Work to include removal of existing free-standing showerhead, surface preparation, all labor, materials, mounting, connections, testing, and compliance with manufacturer instructions/anchor installation to deck and local codes. |  |  | 1 | Each | 0 | 0
A-4 | Landscaping Design Consultant | The scope of work involves the design of landscaping for existing waterproofed planters. The work includes preparing a comprehensive plan that ensures compliance with all city greenery requirements and applicable codes, and verifies that all plant selections, layouts, and materials are appropriate for the planters’ conditions and long-term health. The consultant shall be a qualified and/or licensed landscape architect or designer. |  |  | 1 | Each | 0 | 0
A-5 | Pebble Tec Finish | The scope of work involves application of Pebble Tec Finishes in-liu of the base bid (Diamond Brite). Color selection by Owner. |  |  | 1 | Lump Sum | 0 | 0
Unit Costs for Typical Repairs:
ITEM # | REPAIR | DESCRIPTION |  |  | QTY TYPE |  | UNIT COST
U-1 | Stucco Repair | Restore damaged stucco or application of stucco to repaired area. |  |  | SqFt |  | 0
U-2 | Top of Slab Repair | Restore top of slab concrete/topping. |  |  | SqFt |  | 0
U-3 | Overhead Slab Repair | Restore damaged overhead concrete. |  |  | SqFt |  | 0
U-4 | Edge of Slab Repair | Restore edge of slab concrete. |  |  | SqFt |  | 0
U-5 | Vertical/Wall Concrete Repair | Restore vertical/wall concrete. |  |  | SqFt |  | 0
U-6 | Concrete Column Repair | Restore concrete column. |  |  | SqFt |  | 0
U-7 | Concrete Beam Repair | Restore concrete beam. |  |  | SqFt |  | 0
U-8 | Spot Repair | Restore concrete spot repair (e.g., shallow rebar, rebar chair, etc.) |  |  | Each |  | 0
U-9 | CMU Joint Repair | Restore joint at CMU block. |  |  | Linear Feet |  | 0
U-10 | CMU Block Repair | Restore CMU block. |  |  | Each |  | 0
U-11 | Epoxy Injection | Epoxy inject crack repair. |  |  | Linear Feet |  | 0
U-12 | Gravity Fed | Gravity fed crack repair. |  |  | Linear Feet |  | 0
U-13 | Hydrophobic Injections | Restore cracked concrete |  |  | Linear Feet |  | 0
U-14 | Painting | Paint area. |  |  | SqFt |  | 0
U-15 | Hourly Labor Rate | Labor Rate (Include OH&P, Taxes, & Insurance) |  |  | Hour |  | 0
U-16 | Material Cost Plus | Mark-up percentage on Material |  |  | % |  | %
U-17 | Sub-Contractor Cost Plus | Mark-up percentage on Sub-Contractor |  |  | % |  | %
U-18 | Equipment Rental Cost Plus | Mark-up percentage on Equipment |  |  | % |  | %
U-19 | General Conditions | Mark-up percentage on Change Orders |  |  | % |  | %
U-20 | Combined Maximum Mark-Up | Maximum combined mark-up percentage to be applied under conditions above. |  |  | % |  | %
Note: All activities mentioned herein include all required materials unless otherwise noted. See drawings for the repair schedule and general project scope of work. All quantities presented are to be used as a budgetary estimate. Contractor shall field verify quantities and obtain EOR review & approval for large discrepancies. Contractor shall provide EOR/Owner with backup documentation if requested to substantiate change order costs when mark-ups are applied. The basis for Unit Cost repairs beyond the contracted scope of work shall be billed at the base unit per location (rounded up to the nearest square foot, linear foot, cubic foot) unless otherwise agreed upon by Owner.