## Intra_Roof_PayApp Log
Marcon Forensics - Payment Application Tracking Log
Project: | Upton- Recert Repairs | [5 empty] | Last Edited By: | Jho
Item # | Description | Cost | Status | Date Received | Date Approved | Notes | Date: | 2025-06-27
| Pay App #1 | 84239.71 | Approved | 2025-02-13 | 2025-02-19
| Pay App #2 | 81105.25 | Approved | 2025-04-23 | 2025-04-23
| Pay App #3 | 195621.78 | Approved | 2025-05-01 | 2025-05-13
| Pay App #4 | 89476.4 | Approved | 2025-05-30 | 2025-06-02 | Includes retainage
| Pay App #5 | 11950 | Approved | 2025-06-27 | 2025-06-27 | CO #06
| CO #1 - Scuppers Enlarged (4) 16"x4" | 3599.6 | Approved | N/A | N/A
| CO#2 - Permit Overrun | 5290.09 | Approved | N/A | N/A
| CO#3 - Coping Cap 316 Stainless steel | 2429.87 | Approved | N/A | N/A
| CO#4 - Temp of Concrete & Cut open 20" x 5" | 4986.75 | Approved | N/A | N/A
| CO#5 - Ventilator Repairs | 12885 | Approved | N/A | N/A
| CO#6 - 28 electrical repairs | 11950 | Approved | N/A | N/A
462393.14
|  | 41141.31 |  | 421251.83

## Pay App #1
A | B |  |  |  | C | D | E | F | G |  | H | I | i
Work Completed
Item No. | Description of Work | unit price | Estimated quantity | Unit | Scheduled Value | From Previous Application (D+E) | This Period | Materials Presently Stored (No In D or E) | Total Completed and Stored To Date (D+E+F) | % (G/C) | Balance to Finish (C-G) | Retainage (If Variable Rate) 10% | Retainage this period
Base Bid General
1 | Permit Allowance | 16886.27 |  |  | 16886.27 | 0 | 16886.27 | 0 | 16886.27 | 100% | 0 |  | 0
2 | General Condtions | 73913.88 |  |  | 73913.88 | 0 | 67353.44 | 0 | 67353.44 | 91.12% | 6560.44 |  | 0
3 | Payment and Performance Bond | 2% |  |  | 0.02 | 0 |  | 0 | 0 |  | 0.02 |  | 0
4 | Mobilization | Included in 2.0 |  |  | Included in 2.0 | 0 |  | 0 | 0
5 | De-Mobilization and Clean Up | Included in 2.0 |  |  | Included in 2.0 | 0 |  | 0 | 0 |  |  |  | 0
6 | Parapet Wall Repairs | Not Included |  |  | Not Included | 0 |  | 0 | 0 |  |  |  | 0
7 | Remove Existing Flat Roofing System Down to Structural Slab | 19122.1 |  |  | 19122.1 | 0 |  | 0 | 0 |  | 19122.1 |  | 0
8 | Install Polyiso Insulation | 31205.03 |  |  | 31205.03 | 0 |  | 0 | 0 |  | 31205.03 |  | 0
9 | Installation of 60 MIL TPO Membrane System | 36777.53 |  |  | 36777.53 | 0 |  | 0 | 0 |  | 36777.53 |  | 0
10 | Installation of TPO-type Walkway Pads | 8866.34 |  |  | 8866.34 | 0 |  | 0 | 0 |  | 8866.34 |  | 0
11 | Re-install drains | 1278.94 |  |  | 1278.94 | 0 |  | 0 | 0 |  | 1278.94 |  | 0
12 | Remove and Replace of Stucco | Not Included |  |  | Not Included | 0 |  | 0 | 0 |  |  |  | 0
13 | Install coping cap for parapet wall | 25098.83 |  |  | 25098.83 | 0 |  | 0 | 0 |  | 25098.83 |  | 0
14 | New "Upsized" overflow scuppers | 5401.13 |  |  | 5401.13 | 0 |  | 0 | 0 |  | 5401.13 |  | 0
15 | Removal & Replacement of existing VTR's | 1374.62 |  |  | 1374.62 | 0 |  | 0 | 0 |  | 1374.62 |  | 0
16 | Metal Drip Edge | 2658.85 |  |  | 2658.85 | 0 |  | 0 | 0 |  | 2658.85 |  | 0
17 | Installation of new aluminum Adjustable Stands | 162500 |  |  | 162500 | 0 |  | 0 | 0 |  | 162500 |  | 0
18 | Refrigerant Piping Insulation | 6240 |  |  | 6240 | 0 |  | 0 | 0 |  | 6240 |  | 0
19 | Removal and Replacement of Local HVAC Disconnects and Wiring | 835 |  |  | 835 | 0 |  | 0 | 0 |  | 835 |  | 0
20 | Removal and Replacement of Local HVAC Junction boxes Supports | 11520 |  |  | 11520 | 0 |  | 0 | 0 |  | 11520 |  | 0
21 | Installation of Hurricane tie-down kits | 11520 |  |  | 11520 | 0 |  | 0 | 0 |  | 11520 |  | 0
22 | Allowances for miscellaneous | 6000 |  |  | 6000 | 0 |  | 0 | 0 |  | 6000 |  | 0
Totals: |  | 421198.54 | 0 | 0 | 421198.54 | 0 | 84239.71 | 0 | 84239.71 | 20% | 336958.83 | 0 | 0
Change order total |  | Line item #28
Totals: |  |  |  |  | 421198.54 | 0 | 84239.71 | 0 | 84239.71 |  | 336958.83 | 0 | 0
Current Payment Due | [7 empty] | 84239.71 |  |  |  |  | E-M

## Pay App #2
A | B |  |  |  | C | D | E | F | G |  | H | I | i
Work Completed
Item No. | Description of Work | unit price | Estimated quantity | Unit | Scheduled Value | From Previous Application (D+E) | This Period | Materials Presently Stored (No In D or E) | Total Completed and Stored To Date (D+E+F) | % (G/C) | Balance to Finish (C-G) | Retainage (If Variable Rate) 10% | Retainage PERIOD
Base Bid General
1 | Permit Allowance | 16886.27 |  |  | 16886.27 | 16886.27 |  | 0 | 16886.27 | 100% | 0 |  | 0
2 | General Condtions | 73913.88 |  |  | 73913.88 | 67353.44 |  | 0 | 67353.44 | 91.12% | 6560.44 |  | 0
3 | Payment and Performance Bond | 2% |  |  | 0.02 | 0 |  | 0 | 0 | 0% | 0.02 |  | 0
4 | Mobilization | Included in 2.0 |  |  | Included in 2.0 | 0 |  | 0 | 0
5 | De-Mobilization and Clean Up | Included in 2.0 |  |  | Included in 2.0 | 0 |  | 0 | 0 |  |  |  | 0
6 | Parapet Wall Repairs | Not Included |  |  | Not Included | 0 |  | 0 | 0 |  |  |  | 0
7 | Remove Existing Flat Roofing System Down to Structural Slab | 19122.1 |  |  | 19122.1 | 0 | 19122.1 | 0 | 19122.1 | 100% | 0 |  | 1912.21
8 | Install Polyiso Insulation | 31205.03 |  |  | 31205.03 | 0 | 31205.03 | 0 | 31205.03 | 100% | 0 |  | 3120.503
9 | Installation of 60 MIL TPO Membrane System | 36777.53 |  |  | 36777.53 | 0 | 33912.57 | 0 | 33912.57 | 92.21% | 2864.96 |  | 3391.257
10 | Installation of TPO-type Walkway Pads | 8866.34 |  |  | 8866.34 | 0 |  | 0 | 0 |  | 8866.34 |  | 0
11 | Re-install drains | 1278.94 |  |  | 1278.94 | 0 |  | 0 | 0 |  | 1278.94 |  | 0
12 | Remove and Replace of Stucco | Not Included |  |  | Not Included | 0 |  | 0 | 0 |  |  |  | 0
13 | Install coping cap for parapet wall | 25098.83 |  |  | 25098.83 | 0 |  | 0 | 0 |  | 25098.83 |  | 0
14 | New "Upsized" overflow scuppers | 5401.13 |  |  | 5401.13 | 0 |  | 0 | 0 |  | 5401.13 |  | 0
15 | Removal & Replacement of existing VTR's | 1374.62 |  |  | 1374.62 | 0 |  | 0 | 0 |  | 1374.62 |  | 0
16 | Metal Drip Edge | 2658.85 |  |  | 2658.85 | 0 |  | 0 | 0 |  | 2658.85 |  | 0
17 | Installation of new aluminum Adjustable Stands | 162500 |  |  | 162500 | 0 |  | 0 | 0 |  | 162500 |  | 0
18 | Refrigerant Piping Insulation | 6240 |  |  | 6240 | 0 |  | 0 | 0 |  | 6240 |  | 0
19 | Removal and Replacement of Local HVAC Disconnects and Wiring | 835 |  |  | 835 | 0 |  | 0 | 0 |  | 835 |  | 0
20 | Removal and Replacement of Local HVAC Junction boxes Supports | 11520 |  |  | 11520 | 0 |  | 0 | 0 |  | 11520 |  | 0
21 | Installation of Hurricane tie-down kits | 11520 |  |  | 11520 | 0 |  | 0 | 0 |  | 11520 |  | 0
22 | Allowances for miscellaneous | 6000 |  |  | 6000 | 0 |  | 0 | 0 |  | 6000 |  | 0
Totals: |  | 421198.54 | 0 | 0 | 421198.54 | 84239.71 | 84239.7 | 0 | 168479.41 | 21.97% | 252719.13 | 0 | 8423.97
Change Orders
23 | Scuppers Enlarged (4) 16"x4" |  |  |  | 3599 | 0 |  | 0 |  | 0% | 3599 |  | 0
24 | Permit Overrun |  |  |  | 5290.09 | 0 | 5290.09 | 0 | 5290.09 | 100% | 0 |  | 0
25 | Coping Cap 316 Stainless steel |  |  |  | 2429.87 | 0 |  | 0 | 0 | 0% | 2429.87 |  | 0
26 | Temp of Concrete & Cut open 20" x 5" |  |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0
Change order total |  | Line item #28 |  |  | 11318.96 | 0 | 5290.09 | 0 | 5290.09 | 25% | 6028.87 | 0 | 0
Totals: |  |  |  |  | 421198.54 | 84239.71 | 89529.79 | 0 | 173769.5 | 46.97% | 258748 | 0 | 8423.97
Current Payment Due | [7 empty] | 81105.82 |  |  |  |  | E-M

## Pay App #3
A | B |  |  |  | C | D | E | F | G |  | H | I | i
Work Completed
Item No. | Description of Work | unit price | Estimated quantity | Unit | Scheduled Value | From Previous Application (D+E) | This Period | Materials Presently Stored (No In D or E) | Total Completed and Stored To Date (D+E+F) | % (G/C) | Balance to Finish (C-G) | Retainage for this period | Retainage TOTAL
Base Bid General
1 | Permit Allowance | 16886.27 |  |  | 16886.27 | 16886.27 |  | 0 | 16886.27 | 100% | 0 |  | 0
2 | General Condtions | 73913.88 |  |  | 73913.88 | 67353.44 | 6560.44 | 0 | 73913.88 | 100% | 0 |  | 0
3 | Payment and Performance Bond | 2% |  |  | 0.02 | 0 |  | 0 | 0 | 0% | 0.02 |  | 0
4 | Mobilization | Included in 2.0 |  |  | Included in 2.0 | 0 |  | 0 | 0
5 | De-Mobilization and Clean Up | Included in 2.0 |  |  | Included in 2.0 | 0 |  | 0 | 0 |  |  |  | 0
6 | Parapet Wall Repairs | Not Included |  |  | Not Included | 0 |  | 0 | 0 |  |  |  | 0
7 | Remove Existing Flat Roofing System Down to Structural Slab | 19122.1 |  |  | 19122.1 | 19122.1 |  | 0 | 19122.1 | 100% | 0 |  | 1912.21
8 | Install Polyiso Insulation | 31205.03 |  |  | 31205.03 | 31205.03 |  | 0 | 31205.03 | 100% | 0 |  | 3120.503
9 | Installation of 60 MIL TPO Membrane System | 36777.53 |  |  | 36777.53 | 33912.57 | 2864.96 | 0 | 36777.53 | 100% | 0 | 286.496 | 3677.753
10 | Installation of TPO-type Walkway Pads | 8866.34 |  |  | 8866.34 | 0 | 8866.34 | 0 | 8866.34 | 100% | 0 | 886.634 | 886.634
11 | Re-install drains | 1278.94 |  |  | 1278.94 | 0 | 1278.96 | 0 | 1278.96 | 100% | -0.02 | 127.896 | 127.896
12 | Remove and Replace of Stucco | Not Included |  |  | Not Included | 0 |  | 0 | 1278.96 |  |  | 0
13 | Install coping cap for parapet wall | 25098.83 |  |  | 25098.83 | 0 | 25098.83 | 0 | 25098.83 | 100% | 0 | 2509.883 | 2509.883
14 | New "Upsized" overflow scuppers | 5401.13 |  |  | 5401.13 | 0 | 5401.13 | 0 | 5401.13 | 100% | 0 | 540.113 | 540.113
15 | Removal & Replacement of existing VTR's | 1374.62 |  |  | 1374.62 | 0 | 1374.62 | 0 | 1374.62 | 100% | 0 | 137.462 | 137.462
16 | Metal Drip Edge | 2658.85 |  |  | 2658.85 | 0 | 2658.85 | 0 | 2658.85 | 100% | 0 | 265.885 | 265.885
17 | Installation of new aluminum Adjustable Stands | 162500 |  |  | 162500 | 0 | 149420 | 0 | 149420 | 91.95% | 13080 | 14942 | 14942
18 | Refrigerant Piping Insulation | 6240 |  |  | 6240 | 0 | 6240 | 0 | 6240 | 100% | 0 | 624 | 624
19 | Removal and Replacement of Local HVAC Disconnects and Wiring | 835 |  |  | 835 | 0 | 835 | 0 | 835 | 100% | 0 | 83.5 | 83.5
20 | Removal and Replacement of Local HVAC Junction boxes Supports | 11520 |  |  | 11520 | 0 |  | 0 | 0 |  | 11520 |  | 0
21 | Installation of Hurricane tie-down kits | 11520 |  |  | 11520 | 0 |  | 0 | 0 |  | 11520 |  | 0
22 | Allowances for miscellaneous | 6000 |  |  | 6000 | 0 |  | 0 | 0 |  | 6000 |  | 0
Totals: |  | 421198.54 | 0 | 0 | 421198.54 | 168479.41 | 210599.13 | 0 | 380357.5 | 92.8% | 42120 | 20403.869 | 28827.839
Change Orders | [8 empty] | 0
23 | Scuppers Enlarged (4) 16"x4" |  |  |  | 3599 | 0 | 3599.6 | 0 | 3599.6 | 100% |  | 359.96 | 359.96
24 | Permit Overrun |  |  |  | 5290.09 | 5290.09 |  | 0 | 5290.09 | 100% | 0 | 0 | 0
25 | Coping Cap 316 Stainless steel |  |  |  | 2429.87 | 0 | 2429.87 | 0 | 2429.87 | 100% |  | 242.987 | 242.987
26 | Temp of Concrete & Cut open 20" x 5" |  |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0
Change order total |  | Line item #28 |  |  | 11318.96 | 5290.09 | 6029.47 | 0 | 11319.56 | 75% | 0 | 602.947 | 602.947
Totals: |  |  |  |  | 421198.54 | 173769.5 | 216628.6 | 0 | 391677.06 | 90% | 42120 | 21006.816 | 29430.786
Retainage: | [7 empty] | 21006.816 |  |  |  |  | E-M
Current Payment Due | [7 empty] | 195621.784 |  |  |  |  | E-M
BEST = -$52.98

## Pay App #4
A | B |  |  |  | C | D | E | F | G |  | H | I | i
Work Completed
Item No. | Description of Work | unit price | Estimated quantity | Unit | Scheduled Value | From Previous Application (D+E) | This Period | Materials Presently Stored (No In D or E) | Total Completed and Stored To Date (D+E+F) | % (G/C) | Balance to Finish (C-G) | Retainage for this period | Retainage TOTAL
Base Bid General
1 | Permit Allowance | 16886.27 |  |  | 16886.27 | 16886.27 |  | 0 | 16886.27 | 100% | 0 |  | 0
2 | General Condtions | 73913.88 |  |  | 73913.88 | 73913.88 |  | 0 | 73913.88 | 100% | 0 |  | 0
3 | Payment and Performance Bond | 2% |  |  | 0.02 | 0 |  | 0 | 0 | 0% | 0.02 |  | 0
4 | Mobilization | Included in 2.0 |  |  | Included in 2.0 | 0 |  | 0 | 0
5 | De-Mobilization and Clean Up | Included in 2.0 |  |  | Included in 2.0 | 0 |  | 0 | 0 |  |  |  | 0
6 | Parapet Wall Repairs | Not Included |  |  | Not Included | 0 |  | 0 | 0 |  |  |  | 0
7 | Remove Existing Flat Roofing System Down to Structural Slab | 19122.1 |  |  | 19122.1 | 19122.1 |  | 0 | 19122.1 | 100% | 0 |  | 1912.21
8 | Install Polyiso Insulation | 31205.03 |  |  | 31205.03 | 31205.03 |  | 0 | 31205.03 | 100% | 0 |  | 3120.503
9 | Installation of 60 MIL TPO Membrane System | 36777.53 |  |  | 36777.53 | 36777.53 |  | 0 | 36777.53 | 100% | 0 | 0 | 3677.753
10 | Installation of TPO-type Walkway Pads | 8866.34 |  |  | 8866.34 | 8866.34 |  | 0 | 8866.34 | 100% | 0 | 0 | 886.634
11 | Re-install drains | 1278.94 |  |  | 1278.94 | 1278.96 |  | 0 | 1278.96 | 100% | -0.02 | 0 | 127.896
12 | Remove and Replace of Stucco | Not Included |  |  | Not Included | 0 |  | 0 | 0 |  |  | 0
13 | Install coping cap for parapet wall | 25098.83 |  |  | 25098.83 | 25098.83 |  | 0 | 25098.83 | 100% | 0 | 0 | 2509.883
14 | New "Upsized" overflow scuppers | 5401.13 |  |  | 5401.13 | 5401.13 |  | 0 | 5401.13 | 100% | 0 | 0 | 540.113
15 | Removal & Replacement of existing VTR's | 1374.62 |  |  | 1374.62 | 1374.62 |  | 0 | 1374.62 | 100% | 0 | 0 | 137.462
16 | Metal Drip Edge | 2658.85 |  |  | 2658.85 | 2658.85 |  | 0 | 2658.85 | 100% | 0 | 0 | 265.885
17 | Installation of new aluminum Adjustable Stands | 162500 |  |  | 162500 | 149420 | 13080 | 0 | 162500 | 100% | 0 | 1308 | 16250
18 | Refrigerant Piping Insulation | 6240 |  |  | 6240 | 6240 |  | 0 | 6240 | 100% | 0 | 0 | 624
19 | Removal and Replacement of Local HVAC Disconnects and Wiring | 835 |  |  | 835 | 835 |  | 0 | 835 | 100% | 0 | 0 | 83.5
20 | Removal and Replacement of Local HVAC Junction boxes Supports | 11520 |  |  | 11520 | 0 | 11520 | 0 | 11520 |  | 0 |  | 1152
21 | Installation of Hurricane tie-down kits | 11520 |  |  | 11520 | 0 | 11520 | 0 | 11520 |  | 0 |  | 1152
22 | Allowances for miscellaneous | 6000 |  |  | 6000 | 0 | 6000 | 0 | 6000 |  | 0 |  | 600
Totals: |  | 421198.54 | 0 | 0 | 421198.54 | 379078.54 | 42120 | 0 | 421198.54 | 93.33% | 1.819e-14 | 1308 | 33039.839
Change Orders | [8 empty] | 0
23 | Scuppers Enlarged (4) 16"x4" |  |  |  | 3599 | 3599 |  | 0 | 3599 | 100% |  | 0 | 0
24 | Permit Overrun |  |  |  | 5290.09 | 10580.18 |  | 0 | 10580.18 | 200% | 0 | 0 | 0
25 | Coping Cap 316 Stainless steel |  |  |  | 2429.87 | 2429.87 |  | 0 | 2429.87 | 100% |  | 0 | 0
26 | Temp of Concrete & Cut open 20" x 5" | [5 empty] | 4986.75 | 0 | 4986.75 |  | 0 |  | 498.675
12885
Change order total |  | Line item #28 |  |  | 11318.96 | 16609.05 | 4986.75 | 0 | 21595.8 | 100% | 0 | 0 | 498.675
Totals: |  |  |  |  | 421198.54 | 235159.12 | 59991.75 | 0 | 442794.34 | 90% | 1.819e-14 | 1308 | 33538.514
Retainage: | [7 empty] | 1308 |  |  |  |  | E-M
Current Payment Due | [7 empty] | 58683.75 |  |  |  |  | E-M

## Pay App #5
A | B |  |  |  | C | D | E | F | G |  | H | I | i
Work Completed
Item No. | Description of Work | unit price | Estimated quantity | Unit | Scheduled Value | From Previous Application (D+E) | This Period | Materials Presently Stored (No In D or E) | Total Completed and Stored To Date (D+E+F) | % (G/C) | Balance to Finish (C-G) | Retainage for this period | Retainage TOTAL
Base Bid General
1 | Permit Allowance | 16886.27 |  |  | 16886.27 | 16886.27 |  | 0 | 16886.27 | 100% | 0 |  | 0
2 | General Condtions | 73913.88 |  |  | 73913.88 | 73913.88 |  | 0 | 73913.88 | 100% | 0 |  | 0
3 | Payment and Performance Bond | 2% |  |  | 0.02 | 0 |  | 0 | 0 | 0% | 0.02 |  | 0
4 | Mobilization | Included in 2.0 |  |  | Included in 2.0 | 0 |  | 0 | 0
5 | De-Mobilization and Clean Up | Included in 2.0 |  |  | Included in 2.0 | 0 |  | 0 | 0 |  |  |  | 0
6 | Parapet Wall Repairs | Not Included |  |  | Not Included | 0 |  | 0 | 0 |  |  |  | 0
7 | Remove Existing Flat Roofing System Down to Structural Slab | 19122.1 |  |  | 19122.1 | 19122.1 |  | 0 | 19122.1 | 100% | 0 |  | 1912.21
8 | Install Polyiso Insulation | 31205.03 |  |  | 31205.03 | 31205.03 |  | 0 | 31205.03 | 100% | 0 |  | 3120.503
9 | Installation of 60 MIL TPO Membrane System | 36777.53 |  |  | 36777.53 | 36777.53 |  | 0 | 36777.53 | 100% | 0 | 0 | 3677.753
10 | Installation of TPO-type Walkway Pads | 8866.34 |  |  | 8866.34 | 8866.34 |  | 0 | 8866.34 | 100% | 0 | 0 | 886.634
11 | Re-install drains | 1278.94 |  |  | 1278.94 | 1278.96 |  | 0 | 1278.96 | 100% | -0.02 | 0 | 127.896
12 | Remove and Replace of Stucco | Not Included |  |  | Not Included | 0 |  | 0 | 0 |  |  | 0
13 | Install coping cap for parapet wall | 25098.83 |  |  | 25098.83 | 25098.83 |  | 0 | 25098.83 | 100% | 0 | 0 | 2509.883
14 | New "Upsized" overflow scuppers | 5401.13 |  |  | 5401.13 | 5401.13 |  | 0 | 5401.13 | 100% | 0 | 0 | 540.113
15 | Removal & Replacement of existing VTR's | 1374.62 |  |  | 1374.62 | 1374.62 |  | 0 | 1374.62 | 100% | 0 | 0 | 137.462
16 | Metal Drip Edge | 2658.85 |  |  | 2658.85 | 2658.85 |  | 0 | 2658.85 | 100% | 0 | 0 | 265.885
17 | Installation of new aluminum Adjustable Stands | 162500 |  |  | 162500 | 149420 |  | 0 | 149420 | 91.95% | 13080 | 0 | 14942
18 | Refrigerant Piping Insulation | 6240 |  |  | 6240 | 6240 |  | 0 | 6240 | 100% | 0 | 0 | 624
19 | Removal and Replacement of Local HVAC Disconnects and Wiring | 835 |  |  | 835 | 835 |  | 0 | 835 | 100% | 0 | 0 | 83.5
20 | Removal and Replacement of Local HVAC Junction boxes Supports | 11520 |  |  | 11520 | 0 |  | 0 | 0 |  | 11520 |  | 0
21 | Installation of Hurricane tie-down kits | 11520 |  |  | 11520 | 0 |  | 0 | 0 |  | 11520 |  | 0
22 | Allowances for miscellaneous | 6000 |  |  | 6000 | 0 |  | 0 | 0 |  | 6000 |  | 0
Totals: |  | 421198.54 | 0 | 0 | 421198.54 | 379078.54 | 0 | 0 | 379078.54 | 92.8% | 42120 | 0 | 28827.839
Change Orders | [8 empty] | 0
23 | Scuppers Enlarged (4) 16"x4" |  |  |  | 3599.6 | 3599.6 |  | 0 | 3599.6 | 100% |  | 0 | 359.96
24 | Permit Overrun |  |  |  | 5290.09 | 10580.18 |  | 0 | 10580.18 | 200% | 0 | 0
25 | Coping Cap 316 Stainless steel |  |  |  | 2429.87 | 2429.87 |  | 0 | 2429.87 | 100% |  | 0 | 242.987
26 | Temp of Concrete & Cut open 20" x 5" | [6 empty] | 0 | 0 |  | 0 |  | 0
27 | 18 total electrical AC repairs |  |  |  | 11250.09 |  | 11250.09
Change order total |  | Line item #28 |  |  | 22569.65 | 16609.65 | 0 | 0 | 16609.65 | 100% | 0 | 0 | 602.947
Totals: |  |  |  |  | 421198.54 | 235159.72 | 11250.09 | 0 | 395688.19 | 90% | 42120 | 0 | 29430.786
Retainage: | [7 empty] | 0 |  |  |  |  | E-M
Current Payment Due | [7 empty] | 11250.09 |  |  |  |  | E-M