## Bid Form
Intracoastal Tower Condominium - Tower Restoration Project -
Client Information: |  |  | Bidder Information: |  |  |  | Provide min base unit measurements for payment purposes
Address: | 1505 N Riverside Dr Pompano Beach, FL 33062 |  | Company: | COASTAL CONCRETE RESTORATION |  |  | Square Feet
Client: | Intracoastal Tower Condominium Association |  | Bidder Name: | Keith Benhayon |  |  | Cubic Feet
P.O.C: | Dave Barbour |  | Title: | Director of Business Development |  |  | Linear Feet
Phone: | (954) 931-8886 |  | Office Phone/Cell: | C: 561-679-5640 / O: 954-427-1994 X 140
Email: | dave@redoaksshutter.com |  | Email: | kbenhayon@coastalpaintingfl.com
Scope of Work:
The repair project encompasses select structural repairs to concrete slabs and framing members, along with replacing the balconies' waterproofing. Additionally, it involves replacing all balcony railings and addressing various stucco repairs. The project will also entail painting the exterior facade of the tower.
Based Bid
ITEM # | AREA | DESCRIPTION |  | ESTIMATED QTY | QTY TYPE | BID AMOUNT
1 | General Conditions | General Field Condition Requirements (Project Manager, Superintendent, Project Coordinator, Quality Control, Community Notifications, Onsite Office/Storage Facilities and Logistics including Lifts, Scaffolding, Dump Fees, Obtaining permits, travel expenses, etc.), All insurances, Freight, Taxes, Contractors OH & P. |  | 1 | LS | 170000
2 | Mobilization | N/A |  | 1 | LS | 7500
3 | Demobilization | N/A |  | 1 | LS | 7500
4 | Overhead Concrete Slab Repairs | In conjunction with other repairs, restore damaged concrete as specified in the contract documents. Cost to include stucco. Priming and painting are to be included within the Painting Scope of Work. |  | 50 | SF | 8750
5 | Top of Slab Concrete Repairs | In conjunction with other repairs, restore damaged concrete as specified in the contract documents. Cost to include coating or paint to match existing. |  | 30 | SF | 3750
6 | Edge of Concrete Slab Repairs | In conjunction with other repairs, restore the damaged edge of concrete slab up to 6" wide as specified in the contract documents. Cost to include stucco. Priming and painting are to be included within the Painting Scope of Work. |  | 500 | LF | 67500
7 | Wall Repairs (Vertical Repairs) | In conjunction with other repairs, restore damaged concrete as specified in the contract documents. Reference the Repair Schedule. Cost to include stucco. Priming and painting are to be included within the Painting Scope of Work. |  | 50 | SF | 7750
8 | Partial Concrete Column Repairs | In conjunction with other repairs, restore damaged concrete as specified in the contract documents. Cost to include stucco. Priming and painting are to be included within the Painting Scope of Work. |  | 40 | CF | 15000
9 | Epoxy Injection for Crack Repair | In conjunction with other repairs, restore damaged concrete as specified in contract documents. Priming and painting are to be included in the Painting Scope of Work. |  | 100 | LF | 5500
10 | Crack repair by Gravity Feed | In conjunction with other repairs, restore damaged concrete as specified in contract documents. Priming and painting are to be included in the Painting Scope of Work. |  | 200 | LF | 22500
11 | Stucco Repair | In conjunction with other repairs, restore damaged stucco as specified on the contract documents. Reference the Repair Schedule. Priming and painting are to be included within the Painting Scope of Work. |  | 2150 | SF | 75250
12 | Stucco Crack Repair | In conjunction with other repairs, restore damaged stucco as specified on the contract documents. Reference the Repair Schedule. Priming and painting are to be included within the Painting Scope of Work. |  | 500 | LF | 15000
13 | Shutter Removal, Storage, & Reinstallation | Work includes the removal of existing shutters and previous shutter fasteners on all balconies. Work includes storage of shutters and reinstallation if possible. |  | 1 | hr | 55
14 | Shutter Removal and Disposal | Work includes the removal of existing shutters. New shutters to be reinstalled at cost to unit owner. |  | 1 | LS | 13800
15 | Tile Removal & Disposal on the Balconies | Work includes removal and disposal of existing tile finishes on all balconies in preparation for the waterproofing replacement. Estimated 11,250 SF. Contractor to field verify quantity. |  | 1 | LS | 45000
16 | Removal of Balcony Enclosure | Work includes removal and disposal of existing balcony enclosures on all the balconies. Estimated 2,700 LF. Contractor to field verify quantity. |  | 1 | LS | 27200
17 | Replacement of Balcony Enclosure (Glass Railing) | Work includes Installation of new balcony railing as stated on the contract drawings(to be determine by Association). Estimated 2,700 LF. Contractor to field verify quantity. |  | 1 | LS | TBD
18 | Replacement of Balcony Enclosure (Standard aluminium embedded railing) | Work includes Installation of new balcony railing and enclosures as stated on the contract drawings(to be determine by Association). Estimated 2,700 LF. Contractor to field verify quantity. |  | 1 | LS | 555000
19 | Waterproofing Replacement of the Balconies | Work includes removal and disposal of existing waterproofing on all balconies. Work includes substrate preparation in accordance with manufacturer requirements. Work includes the installation/applications of the new waterproofing system (Sikalastic 710 Base, Sikalastic 715 Top & SikaTop Seal 107) as stated on the design specifications & drawings. Estimated area of 11,250 Sqft, contractor is responsible for measurments on site. |  | 1 | LS | 202500
20 | Paint Preparation | Surface preparation in accordance with manufacturer requirments including but not limited to, pressure washing, removal/replacement of cracked and worn sealants and caulking. |  | 1 | LS | 5000
21 | Tower Paint Application | Paint selection and application shall be in accordance with the provided specifications and meet or exceed the warranty requirments. Application shall be in accordance with the manufacturer requirements. The paint color is to be determined by ownership prior to application. |  | 1 | LS | 165000
22 | Permit Fees | At Cost |  | 1 | LS | 5%
23 | Payment and Performance Bond | N/A |  | 1 | LS | 2.75%
LEGEND: SF – Square Feet, LS – Lump Sum, EA – Each, LF – Linear Feet, CF – Cubic Feet
TOTAL COST (BASE BID): |  |  |  |  | 1419555.0775
ESTIMATED PROJECT DURATION (BASE BID): |  |  |  |  | 12 Months
1. All activities mentioned herein include all required materials unless otherwise noted. See Drawings for the repair schedule and general project scope of work. 2. All quantities presented are to be used as a budgetary estimate. Contractor shall field verify quantities and obtain Engineer review/approval for large discrepancies.
Unit Cost Items
ITEM # | AREA | DESCRIPTION |  | ESTIMATED QTY | QTY TYPE | UNIT COST
U-1 | Partial Concrete top of Slab Repairs | Restore damaged on top of concrete slab |  | 1 | SF | 125
U-2 | Edge of Slab Repair | Restore damaged slab edge concrete |  | 1 | LF | 135
U-3 | Overhead Slab Repairs | Restore damaged overhead concrete |  | 1 | SF | 175
U-4 | Vertical/Wall Repair | Restore vertical damaged concrete |  | 1 | SF | 155
U-5 | Partial Concrete Beam Repairs | Restore damaged concrete beams/joists |  | 1 | CF | 375
U-6 | Partial Concrete Column Repairs | Restore damaged concrete column |  | 1 | CF | 375
U-7 | Full Depth Slab Repair | Restore damage concrete slab |  | 1 | SF | 160
U-8 | Concrete crack repair via epoxy injection | Repair cracks at concrete |  | 1 | LF | 55
U-9 | Crack repair by Gravity Feed | Repair cracks at concrete |  | 1 | LF | 45
U-10 | Stucco Repair | Stucco repaired area |  | 1 | SF | 35
U-11 | Stucco Crack Repair | Repair cracks at stucco |  | 1 | LF | 30
U-12 | Painting | Paint repaired area |  | 1 | SF | 2
U-13 | Waterproofing installation of the balconies | Remove existing waterproofing and install a new one as specified on the contract documents. |  | 1 | SF | 3.5
U-14 | Tile removal at balconies | Removal of existing tiles for waterproofing replacement |  | 1 | SF | 4
U-15 | Hourly Labor Rate | Standard hourly rate including OH&P, taxes, and insurance. |  | 1 | Hour | 55
U-16 | Material Cost Plus | Mark-up percentage on materials |  | 1 | % | 10%
U-17 | Subcontractor Cost Plus | Mark-up percentage on Subcontractors |  | 1 | % | 10%
U-18 | Equipment Rental Cost Plus | Mark-up percentage on Equipment |  | 1 | % | 10%

## Contractor "A"
Contractor "A"
General Project Information:
Project Name & Location: | Intracoastal Tower Condominium | 1505 N Riverside Dr Pompano Beach, FL 33062
Scope of Work: | The repair project encompasses select structural repairs to concrete slabs and framing members, along with replacing the balconies' waterproofing. Additionally, it involves replacing all balcony railings and addressing various stucco repairs. The project will also entail painting the exterior facade of the tower.
Company: | Coastal Painting of South Florida
Bidder Name: | Keith Benhayon
Approximate Days of Construction: | 12 months
Questions & Answers:
Question: | No. 1 Answers: | No. 2 Answers: | No. 3 Answers:
Fill in the Subcontractor, the indicated indicated work and contact information: | Name: Metal Supply and Machining, Inc | Name: Master Touch | Name:
| Area of work: Railings | Area of work: Pool | Area of work:
| Address/Phone/email: 1304 Gwenzell Ave., Delray Beach, FL 33444/561.276.4941 (office) | Address/Phone/email: 11860 Wiles Road/5616746909/office@mastertouchpools.com | Address/Phone/email:
Insurance: | Liability Insurance Carrier Name: Security National
Liability Insurance Limits: $1M/2M
Workers Compensation Carrier Name: Bridgefield Employers
Workers Compensation Limits: $1M
Do you provide a warranty on your work? If yes, please detail the terms. | Concrete Repair/Restoration:1 year
Stucco Repair/Restoration: 1year
Painiting:1 year isntallation 10 year product warranty thru paint manufacturer
Describe your policy and contingency for any interior damage sustained to a unit as a result of repair work | Work areas inside dust walls are to be free of personal belongings.
What is the anticipated project start date (month and year) should you be awarded the project? | 2024-10-01
Does your company have a hurricane preparedness plan? | Yes,
In the event that the actual repair quantities exceed the contracted scope of work, please describe your proposed method for the inclusion of General Conditions (GC) into the Change Orders. (For example, after exceeding 10% of additional quantities for a repair, a GC of 20% will be added to the Change Order.)