## IntraTower_PayApp Log
Marcon Forensics - Payment Application Tracking Log - Intra Tower + Roof repairs
Project: | Upton- Recert Repairs | [5 empty] | Last Edited By: | Jholyn
Item # | Description | Cost | Status | Date Received | Date Approved | Notes | Date: | 2025-10-20
1 | Pay App #1 | 133875 | Approved | 2025-02-27 | 2025-03-02 | N/a
2 | Pay App #2 | 58666.83 | Approved | 2025-05-05 | 2025-05-10 | N/a
3 | Pay App #3 | 18096.3 | Approved | 2025-07-02 | 2025-07-07 | N/a
4 | Pay App #4 | 25912.989 | Approved | 2025-06-30 | 2025-07-11 | N/a
5 | Pay App #5 | 63000 | Approved | 2025-07-31 | 2025-08-01 | N/a
6 | Pay App #6 | 114390 | Approved | 2025-10-07 | 2025-10-08 | Waterproofing and new 3-coat stucco are still pending. Marcon is approving payment based on the board’s approval for full payment for this phase.
7 | Pay App #7 | 59199.85 | Approved | 2025-10-13 | 2025-10-20 | N/a

## Pay App #1
A | B |  |  |  | C | D | E | F | G |  | H | I | i
Work Completed
Item No. | Description of Work | unit price | Estimated quantity | Unit | Scheduled Value | From Previous Application (D+E) | This Period | Materials Presently Stored (No In D or E) | Total Completed and Stored To Date (D+E+F) | % (G/C) | Balance to Finish (C-G) | Retainage (If Variable Rate) 10% | Retainage this period
Base Bid General
1 | General Condtions | 100000 | 1 | LS | 100000 | 0 |  | 0 | 0 | 0% | 100000 |  | 0
2 | Mobilization | 40000 | 1 | LS | 40000 | 0 |  | 0 | 0 | 0% | 40000 |  | 0
3 | De-Mobilization | 30000 | 1 | LS | 30000 | 0 |  | 0 | 0 | 0% | 30000 |  | 0
4 | Overhead Concrete Slab Repairs | 140 | 50 | SF | 7000 | 0 |  | 0 | 0 | 0%
5 | Top of Slab Concrete Repairs | 125 | 30 | SF | 3750 | 0 |  | 0 | 0 | 0% |  |  | 0
6 | Edge of Concrete Slab Repairs | 135 | 500 | LF | 67500 | 0 |  | 0 | 0 | 0% |  |  | 0
7 | Wall Repairs (Vertical Repairs) | 100 | 50 | SF | 5000 | 0 |  | 0 | 0 | 0% | 5000 |  | 0
8 | Partial Concrete Column Repairs | 425 | 40 | CF | 17000 | 0 |  | 0 | 0 | 0% | 17000 |  | 0
9 | Epoxy Injection for Crack Repairs | 75 | 100 | LF | 7500 | 0 |  | 0 | 0 | 0% | 7500 |  | 0
10 | Crack Repair by Gravity Feed | 48 | 200 | LF | 9600 | 0 |  | 0 | 0 | 0% | 9600 |  | 0
11 | Stucco Repair | 30 | 2150 | SF | 64500 | 0 |  | 0 | 0 | 0% | 64500 |  | 0
12 | Stucco Crack Repair | 22 | 500 | LF | 11000 | 0 |  | 0 | 0 | 0% |  |  | 0
13 | Shutter Removal, Storage, & reinstallation | 115 | 1 | LF | 115 | 0 |  | 0 | 0 | 0% | 115 |  | 0
14 | Shutter Removal and Disposal | 50 | 1 | LF | 50 | 0 |  | 0 | 0 | 0% | 50 |  | 0
15 | Tile Removal & Disposal on the Balconies | 6.5 | 11250 | SF | 73125 | 0 |  | 0 | 0 | 0% | 73125 |  | 0
16 | Removal of Balcony enclosures | 45 | 2700 | LF | 121500 | 0 |  | 0 | 0 | 0% | 121500 | 0 | 0
17 | Replacement of Balcony Englosures (Glass) |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
18 | Replacement of Balcony Englosures (Standard) | 425000 | 1 | LS | 425000 | 0 | 148750 | 0 | 148750 | 35% | 276250 | -0.35 | 14875
19 | Waterproofing Replacement of the Balconies | 22 | 11250 | SF | 247500 | 0 |  | 0 | 0 | 0% | 247500 | 0 | 0
20 | Waterproofing of Pool Deck | 12 | 12000 | SF | 144000 | 0 |  | 0 | 0 | 0% | 144000 | 0 | 0
21 | Waterproofing of Planters | 19995 | 1 | LS | 19995 | 0 |  | 0 | 0 | 0% | 19995 | 0 | 0
22 | Expansion Joint repairs at Pool Deck | 250 | 230 | LF | 57500 |  |  |  |  | 0% | 57500 | 0
23 | Expansion Joint bldg to Pool Deck Slab | 75 | 130 | LF | 9750 |  |  |  |  | 0% | 9750 | 0
24 | Paint Preparation | 26550 | 1 | LS | 26550 |  |  |  |  | 0% | 26550 | 0
25 | Tower Paint Application | 80442 | 1 | LS | 80442 |  |  |  |  | 0% | 80442 | 0
26 | Permit Fees | 1 | 40114 | LS | 40114 |  |  |  |  | 0% | 40114
27 | Payment and performance Bond |  |  |  | 0 | [5 empty] | 0
28 | Additional/Alternate Estimate Allowances |  |  |  | 0 | [5 empty] | 0
29 | Replacement of SGD (Dust wall) | 995 |  | LF | 0 | 0 |  | 0 | 0 |  | 0 |  | 0
Totals: |  |  |  |  | 1608491 | 0 | 148750 | 0 | 148750 | 20% | 1370491 | -0.35 | 14875
31 | Partial Concrete top of Slab Repairs | 125 |  | SF | 0
32 | Edge of slab repairs | 135 |  | LF | 0
33 | Overhead slab repair | 135 |  | SF | 0
34 | Vertical/wall repiar | 100 |  | SF | 0
35 | Partial Concrete Beam repair | 425 |  | CF | 0
36 | Partial Concrete Column Repair | 400 |  | CF | 0
37 | Full Depth Slab Repair | 140 |  | SF | 0
38 | Concrete crack repair epoxy inject | 75 |  | LF | 0
39 | Concrete crack repair Gravity Feed | 48 |  | LF | 0
40 | Stucco repair | 30 |  | SF | 0
41 | Stucco crack repair | 22 |  | LF | 0
42 | painiting repaired area | 5 |  | SF | 0
43 | Waterproofing installation on the balcony | 22 |  | SF | 0
44 | Tile removal at balconies | 7.5 |  | SF | 0
45 | Hourly Labor Rate | 85 |  | HR | 0
46 | Roof Repairs - Time/Labor | 85 |  | HR | 0
47 | Material Cost Plus | 10% |  | PERC | 0
48 | Roof Repairs - Material Cost | 4086.7 |  | LS | 0
49 | Roof Repairs - Material Cost Plus | 10% |  | PERC | 0
50 | Subcontractor Cost Plus | 10% |  | PERC | 0
51 | Equipment Rental Cost Plus | 10% |  | PERC
52 | Replacement of Balcony Enclosure (glass) | 300 |  | LF | 0
53 | Rebar (per contract if needed) | 8.5 |  | LF | 0
0
Change order total |  | Line item #28 |  |  | 0
Totals: |  |  |  |  | 1608491 | 0 | 148750 | 0 | 148750 |  | 1370491 | -0.35 | 14875
Current Payment Due | [7 empty] | 133875 |  |  |  |  | E-M

## Pay App #2
A | B |  |  |  | C | D |  | E | F | G |  | H | I | i
Work Completed
Item No. | Description of Work | unit price | Estimated quantity | Unit | Scheduled Value | From Previous Application (D+E) | Quantity This Period | This Period | Materials Presently Stored (No In D or E) | Total Completed and Stored To Date (D+E+F) | % (G/C) | Balance to Finish (C-G) | Retainage (If Variable Rate) 10% | Retainage this period
Base Bid General
1 | General Condtions | 100000 | 1 | LS | 100000 | 0 |  |  | 0 | 0 | 0% | 100000 |  | 0
2 | Mobilization | 40000 | 1 | LS | 40000 | 0 |  |  | 0 | 0 | 0% | 40000 |  | 0
3 | De-Mobilization | 30000 | 1 | LS | 30000 | 0 |  |  | 0 | 0 | 0% | 30000 |  | 0
4 | Overhead Concrete Slab Repairs | 140 | 50 | SF | 7000 | 0 |  |  | 0 | 0 | 0% |  |  | 0
5 | Top of Slab Concrete Repairs | 125 | 30 | SF | 3750 | 0 |  |  | 0 | 0 | 0% |  |  | 0
6 | Edge of Concrete Slab Repairs | 135 | 500 | LF | 67500 | 0 |  |  | 0 | 0 | 0% |  |  | 0
7 | Wall Repairs (Vertical Repairs) | 100 | 50 | SF | 5000 | 0 |  |  | 0 | 0 | 0% | 5000 |  | 0
8 | Partial Concrete Column Repairs | 425 | 40 | CF | 17000 | 0 |  |  | 0 | 0 | 0% | 17000 |  | 0
9 | Epoxy Injection for Crack Repairs | 75 | 100 | LF | 7500 | 0 |  |  | 0 | 0 | 0% | 7500 |  | 0
10 | Crack Repair by Gravity Feed | 48 | 200 | LF | 9600 | 0 |  |  | 0 | 0 | 0% | 9600 |  | 0
11 | Stucco Repair | 30 | 2150 | SF | 64500 | 0 |  |  | 0 | 0 | 0% | 64500 |  | 0
12 | Stucco Crack Repair | 22 | 500 | LF | 11000 | 0 |  |  | 0 | 0 | 0% |  |  | 0
13 | Shutter Removal, Storage, & reinstallation | 115 | 1 | LF | 115 | 0 |  |  | 0 | 0 | 0% | 115 |  | 0
14 | Shutter Removal and Disposal | 50 | 1 | LF | 50 | 0 |  |  | 0 | 0 | 0% | 50 |  | 0
15 | Tile Removal & Disposal on the Balconies | 6.5 | 11250 | SF | 73125 | 0 |  |  | 0 | 0 | 0% | 73125 |  | 0
16 | Removal of Balcony enclosures | 45 | 2700 | LF | 121500 | 0 |  |  | 0 | 0 | 0% | 121500 |  | 0
17 | Replacement of Balcony Englosures (Glass) | 425000 | 1 | LS | 425000 | 0 |  |  | 0 | 0 | 0% | 425000 |  | 0
18 | Replacement of Balcony Englosures (Standard) | 22 | 11250 | SF | 247500 | 148750 |  |  | 0 | 148750 | 60.1% | 98750 |  | 0
19 | Waterproofing Replacement of the Balconies | 12 | 12000 | SF | 144000 | 0 |  |  | 0 | 0 | 0% | 144000 |  | 0
20 | Waterproofing of Pool Deck | 19995 | 1 | LS | 19995 | 0 |  |  | 0 | 0 | 0% | 19995 |  | 0
21 | Waterproofing of Planters | 250 | 230 | LF | 57500 | 0 |  |  | 0 | 0 | 0% | 57500 |  | 0
22 | Expansion Joint repairs at Pool Deck | 75 | 130 | LF | 9750 | 0 |  |  |  |  | 0% |  |  | 0
23 | Expansion Joint bldg to Pool Deck Slab | 26550 | 1 | LS | 26550 | 0 |  |  |  |  | 0% |  |  | 0
24 | Paint Preparation | 80442 | 1 | LS | 80442 | 0 |  |  |  |  | 0% |  |  | 0
25 | Tower Paint Application | 1 | 40114 | LS | 40114 | 0 |  |  |  |  | 0% |  |  | 0
26 | Permit Fees |  |  |  | 0 | [8 empty] | 0
27 | Payment and performance Bond |  |  |  | 0 | [8 empty] | 0
28 | Additional/Alternate Estimate Allowances |  |  |  | 0 | [8 empty] | 0
29 | Replacement of SGD (Dust wall) | 6000 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0 |  | 0
Totals: |  |  |  |  | 1608491 | 148750 |  | 0 | 0 | 148750 | 20% | 1213635 | 0 | 0
31 | Partial Concrete top of Slab Repairs | 125 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
32 | Edge of slab repairs | 135 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
33 | Overhead slab repair | 135 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
34 | Vertical/wall repiar | 100 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
35 | Partial Concrete Beam repair | 425 |  | CF | 0 | 0 |  |  |  | 0 |  |  |  | 0
36 | Partial Concrete Column Repair | 400 |  | CF | 0 | 0 |  |  |  | 0 |  |  |  | 0
37 | Full Depth Slab Repair | 140 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
38 | Concrete crack repair epoxy inject | 75 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
39 | Concrete crack repair Gravity Feed | 48 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
40 | Stucco repair | 30 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
41 | Stucco crack repair | 22 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
42 | painiting repaired area | 5 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
43 | Waterproofing installation on the balcony | 22 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
44 | Tile removal at balconies | 7.5 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
45 | Hourly Labor Rate | 85 |  | HR | 0 | 0 |  |  |  | 0 |  |  |  | 0
46 | Roof Repairs - Time/Labor | 85 |  | HR | 0 | 0 | 714 | 60690 |  | 60690 |  |  |  | 6069
47 | Material Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 0 |  |  |  | 0
48 | Roof Repairs - Material Cost | 4086.7 |  | LS | 0 | 0 | 1 | 4086.7 |  | 4086.7 |  |  |  | 408.67
49 | Roof Repairs - Material Cost Plus | 10% |  | PERC | 0 | 0 | 10% | 408.67 |  | 408.67 |  |  |  | 40.867
50 | Subcontractor Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 0 |  |  |  | 0
51 | Equipment Rental Cost Plus | 10% |  | PERC | [5 empty] | 0 |  |  |  | 0
52 | Equipment of Balcony Enclosure (glass) | 300 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
53 | Rebar (per contract if needed) | 8.5 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
0 | [13 empty] | 6518.537
Change order total |  | Line item #28 |  |  | 0
Totals: |  |  |  |  | 1608491 | 0 |  | 65185.37 | 0 | 213935.37 |  | 1213635 | 0 | 6518.537
Current Payment Due | [8 empty] | 58666.833 |  |  |  |  | E-M

## Pay App #3
A | B |  |  |  | C | D |  | E | F | G |  | H | I | i
Work Completed
Item No. | Description of Work | unit price | Estimated quantity | Unit | Scheduled Value | From Previous Application (D+E) | Quantity This Period | This Period | Materials Presently Stored (No In D or E) | Total Completed and Stored To Date (D+E+F) | % (G/C) | Balance to Finish (C-G) | Retainage (If Variable Rate) 10% | Retainage this period
Base Bid General
1 | General Condtions | 100000 | 1 | LS | 100000 | 0 |  |  | 0 | 0 | 0% | 100000 |  | 0
2 | Mobilization | 40000 | 1 | LS | 40000 | 0 |  |  | 0 | 0 | 0% | 40000 |  | 0
3 | De-Mobilization | 30000 | 1 | LS | 30000 | 0 |  |  | 0 | 0 | 0% | 30000 |  | 0
4 | Overhead Concrete Slab Repairs | 140 | 50 | SF | 7000 | 0 |  |  | 0 | 0 | 0% |  |  | 0
5 | Top of Slab Concrete Repairs | 125 | 30 | SF | 3750 | 0 |  |  | 0 | 0 | 0% |  |  | 0
6 | Edge of Concrete Slab Repairs | 135 | 500 | LF | 67500 | 0 |  |  | 0 | 0 | 0% |  |  | 0
7 | Wall Repairs (Vertical Repairs) | 100 | 50 | SF | 5000 | 0 |  |  | 0 | 0 | 0% | 5000 |  | 0
8 | Partial Concrete Column Repairs | 425 | 40 | CF | 17000 | 0 |  |  | 0 | 0 | 0% | 17000 |  | 0
9 | Epoxy Injection for Crack Repairs | 75 | 100 | LF | 7500 | 0 |  |  | 0 | 0 | 0% | 7500 |  | 0
10 | Crack Repair by Gravity Feed | 48 | 200 | LF | 9600 | 0 |  |  | 0 | 0 | 0% | 9600 |  | 0
11 | Stucco Repair | 30 | 2150 | SF | 64500 | 0 |  |  | 0 | 0 | 0% | 64500 |  | 0
12 | Stucco Crack Repair | 22 | 500 | LF | 11000 | 0 |  |  | 0 | 0 | 0% |  |  | 0
13 | Shutter Removal, Storage, & reinstallation | 115 | 1 | LF | 115 | 0 |  |  | 0 | 0 | 0% | 115 |  | 0
14 | Shutter Removal and Disposal | 50 | 1 | LF | 50 | 0 |  |  | 0 | 0 | 0% | 50 |  | 0
15 | Tile Removal & Disposal on the Balconies | 6.5 | 11250 | SF | 73125 | 0 |  |  | 0 | 0 | 0% | 73125 |  | 0
16 | Removal of Balcony enclosures | 45 | 2700 | LF | 121500 | 0 |  |  | 0 | 0 | 0% | 121500 |  | 0
17 | Replacement of Balcony Englosures (Glass) | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  | 0 |  | 0
18 | Replacement of Balcony Englosures (Standard) | 425000 | 1 | LS | 425000 | 0 |  |  | 0 | 148750 | 35% | 276250 |  | 0
19 | Waterproofing Replacement of the Balconies | 22 | 11250 | SF | 247500 | 0 |  |  | 0 | 0 | 0% | 247500 |  | 0
20 | Waterproofing of Pool Deck | 12 | 12000 | SF | 144000 | 0 |  |  | 0 | 0 | 0% | 144000 |  | 0
21 | Waterproofing of Planters | 19995 | 1 | LS | 19995 | 0 |  |  | 0 | 0 | 0% | 19995 |  | 0
22 | Expansion Joint repairs at Pool Deck | 250 | 230 | LF | 57500 | 0 |  |  |  | 0 | 0% | 57500 |  | 0
23 | Expansion Joint bldg to Pool Deck Slab | 75 | 130 | LF | 9750 | 0 |  |  |  | 0 | 0% | 9750 |  | 0
24 | Paint Preparation | 26550 | 1 | LS | 26550 | 0 |  |  |  | 0 | 0% | 26550 |  | 0
25 | Tower Paint Application | 80442 | 1 | LS | 80442 | 0 |  |  |  | 0 | 0% | 80442 |  | 0
26 | Permit Fees | 1 | 40114 | LS | 40114 | 0 |  | 20107 |  | 20107 | 50.12% | 20007 |  | 2010.7
27 | Payment and performance Bond |  |  |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0
28 | Additional/Alternate Estimate Allowances |  |  |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0
29 | Replacement of SGD (Dust wall) | 995 |  | LF | 0 | 0 |  |  | 0 | 0 |  | 0 |  | 0
Totals: |  |  |  |  | 1608491 | 0 |  | 20107 | 0 | 168857 | 20% | 1350384 | 0 | 2010.7
31 | Partial Concrete top of Slab Repairs | 125 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
32 | Edge of slab repairs | 135 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
33 | Overhead slab repair | 135 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
34 | Vertical/wall repiar | 100 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
35 | Partial Concrete Beam repair | 425 |  | CF | 0 | 0 |  |  |  | 0 |  |  |  | 0
36 | Partial Concrete Column Repair | 400 |  | CF | 0 | 0 |  |  |  | 0 |  |  |  | 0
37 | Full Depth Slab Repair | 140 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
38 | Concrete crack repair epoxy inject | 75 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
39 | Concrete crack repair Gravity Feed | 48 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
40 | Stucco repair | 30 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
41 | Stucco crack repair | 22 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
42 | painiting repaired area | 5 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
43 | Waterproofing installation on the balcony | 22 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
44 | Tile removal at balconies | 7.5 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
45 | Hourly Labor Rate | 85 |  | HR | 0 | 0 |  |  |  | 0 |  |  |  | 0
46 | Roof Repairs - Time/Labor | 85 |  | HR | 0 | 60690 |  |  |  | 60690 |  |  |  | 0
47 | Material Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 0 |  |  |  | 0
48 | Roof Repairs - Material Cost | 4086.7 |  | LS | 0 | 4086.7 |  |  |  | 4086.7 |  |  |  | 0
49 | Roof Repairs - Material Cost Plus | 10% |  | PERC | 0 | 408.67 |  |  |  | 408.67 |  |  |  | 0
50 | Subcontractor Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 0 |  |  |  | 0
51 | Equipment Rental Cost Plus | 10% |  | PERC |  | 0 |  |  |  | 0 |  |  |  | 0
52 | Equipment of Balcony Enclosure (glass) | 300 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
53 | Rebar (per contract if needed) | 8.5 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
0 | [13 empty] | 0
Change order total |  | Line item #28 |  |  | 0
Totals: |  |  |  |  | 1608491 | 65185.37 |  | 20107 | 0 | 234042.37 |  | 1350384 | 0 | 2010.7
Current Payment Due | [8 empty] | 18096.3 |  |  |  |  | E-M

## Pay App #4
A | B |  |  |  | C | D |  | E | F | G |  | H | I | i
Work Completed
Item No. | Description of Work | unit price | Estimated quantity | Unit | Scheduled Value | From Previous Application (D+E) | Quantity This Period | This Period | Materials Presently Stored (No In D or E) | Total Completed and Stored To Date (D+E+F) | % (G/C) | Balance to Finish (C-G) | Retainage (If Variable Rate) 10% | Retainage this period
Base Bid General
1 | General Condtions | 100000 | 1 | LS | 100000 | 0 |  |  | 0 | 0 | 0% | 100000 |  | 0
2 | Mobilization | 40000 | 1 | LS | 40000 | 0 |  |  | 0 | 0 | 0% | 40000 |  | 0
3 | De-Mobilization | 30000 | 1 | LS | 30000 | 0 |  |  | 0 | 0 | 0% | 30000 |  | 0
4 | Overhead Concrete Slab Repairs | 140 | 50 | SF | 7000 | 0 |  |  | 0 | 0 | 0% |  |  | 0
5 | Top of Slab Concrete Repairs | 125 | 30 | SF | 3750 | 0 |  |  | 0 | 0 | 0% |  |  | 0
6 | Edge of Concrete Slab Repairs | 135 | 500 | LF | 67500 | 0 |  |  | 0 | 0 | 0% |  |  | 0
7 | Wall Repairs (Vertical Repairs) | 100 | 50 | SF | 5000 | 0 |  |  | 0 | 0 | 0% | 5000 |  | 0
8 | Partial Concrete Column Repairs | 425 | 40 | CF | 17000 | 0 |  |  | 0 | 0 | 0% | 17000 |  | 0
9 | Epoxy Injection for Crack Repairs | 75 | 100 | LF | 7500 | 0 |  |  | 0 | 0 | 0% | 7500 |  | 0
10 | Crack Repair by Gravity Feed | 48 | 200 | LF | 9600 | 0 |  |  | 0 | 0 | 0% | 9600 |  | 0
11 | Stucco Repair | 30 | 2150 | SF | 64500 | 0 |  |  | 0 | 0 | 0% | 64500 |  | 0
12 | Stucco Crack Repair | 22 | 500 | LF | 11000 | 0 |  |  | 0 | 0 | 0% |  |  | 0
13 | Shutter Removal, Storage, & reinstallation | 115 | 1 | LF | 115 | 0 |  |  | 0 | 0 | 0% | 115 |  | 0
14 | Shutter Removal and Disposal | 50 | 1 | LF | 50 | 0 |  |  | 0 | 0 | 0% | 50 |  | 0
15 | Tile Removal & Disposal on the Balconies | 6.5 | 11250 | SF | 73125 | 0 |  |  | 0 | 0 | 0% | 73125 |  | 0
16 | Removal of Balcony enclosures | 45 | 2700 | LF | 121500 | 0 |  |  | 0 | 0 | 0% | 121500 |  | 0
17 | Replacement of Balcony Englosures (Glass) | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  | 0 |  | 0
18 | Replacement of Balcony Englosures (Standard) | 425000 | 1 | LS | 425000 | 0 |  |  | 0 | 148750 | 35% | 276250 |  | 0
19 | Waterproofing Replacement of the Balconies | 22 | 11250 | SF | 247500 | 0 |  |  | 0 | 0 | 0% | 247500 |  | 0
20 | Waterproofing of Pool Deck | 12 | 12000 | SF | 144000 | 0 |  |  | 0 | 0 | 0% | 144000 |  | 0
21 | Waterproofing of Planters | 19995 | 1 | LS | 19995 | 0 |  |  | 0 | 0 | 0% | 19995 |  | 0
22 | Expansion Joint repairs at Pool Deck | 250 | 230 | LF | 57500 | 0 |  |  |  | 0 | 0% | 57500 |  | 0
23 | Expansion Joint bldg to Pool Deck Slab | 75 | 130 | LF | 9750 | 0 |  |  |  | 0 | 0% | 9750 |  | 0
24 | Paint Preparation | 26550 | 1 | LS | 26550 | 0 |  |  |  | 0 | 0% | 26550 |  | 0
25 | Tower Paint Application | 80442 | 1 | LS | 80442 | 0 |  |  |  | 0 | 0% | 80442 |  | 0
26 | Permit Fees | 1 | 40114 | LS | 40114 | 20107 |  | 20007 |  | 20007 | 49.88% | 20107 |  | 2000.7
| Permit Fees overages |  |  |  | 0 |  |  | 8785.21 |  | 8785.21 |  |  |  | 878.521
27 | Payment and performance Bond |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0
28 | Additional/Alternate Estimate Allowances |  |  |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0
29 | Replacement of SGD (Dust wall) | 995 |  | LF | 0 | 0 |  |  | 0 | 0 |  | 0 |  | 0
Totals: |  |  |  |  | 1608491 | 20107 |  | 28792.21 | 0 | 177542.21 | 20% | 1350484 | 0 | 2879.221
31 | Partial Concrete top of Slab Repairs | 125 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
32 | Edge of slab repairs | 135 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
33 | Overhead slab repair | 135 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
34 | Vertical/wall repiar | 100 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
35 | Partial Concrete Beam repair | 425 |  | CF | 0 | 0 |  |  |  | 0 |  |  |  | 0
36 | Partial Concrete Column Repair | 400 |  | CF | 0 | 0 |  |  |  | 0 |  |  |  | 0
37 | Full Depth Slab Repair | 140 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
38 | Concrete crack repair epoxy inject | 75 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
39 | Concrete crack repair Gravity Feed | 48 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
40 | Stucco repair | 30 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
41 | Stucco crack repair | 22 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
42 | painiting repaired area | 5 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
43 | Waterproofing installation on the balcony | 22 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
44 | Tile removal at balconies | 7.5 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
45 | Hourly Labor Rate | 85 |  | HR | 0 | 0 |  |  |  | 0 |  |  |  | 0
46 | Roof Repairs - Time/Labor | 85 |  | HR | 0 | 0 |  |  |  | 60690 |  |  |  | 0
47 | Material Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 0 |  |  |  | 0
48 | Roof Repairs - Material Cost | 4086.7 |  | LS | 0 | 0 |  |  |  | 4086.7 |  |  |  | 0
49 | Roof Repairs - Material Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 408.67 |  |  |  | 0
50 | Subcontractor Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 0 |  |  |  | 0
51 | Equipment Rental Cost Plus | 10% |  | PERC |  | 0 |  |  |  | 0 |  |  |  | 0
52 | Equipment of Balcony Enclosure (glass) | 300 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
53 | Rebar (per contract if needed) | 8.5 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
0 | [13 empty] | 0
Change order total |  | Line item #28 |  |  | 0
Totals: |  |  |  |  | 1608491 | 0 |  | 28792.21 | 0 | 242727.58 |  | 1350484 | 0 | 2879.221
Current Payment Due | [8 empty] | 25912.989 |  |  |  |  | E-M

## Pay App #5
A | B |  |  |  | C | D |  | E | F | G |  | H | I | i
Work Completed
Item No. | Description of Work | unit price | Estimated quantity | Unit | Scheduled Value | From Previous Application (D+E) | Quantity This Period | This Period | Materials Presently Stored (No In D or E) | Total Completed and Stored To Date (D+E+F) | % (G/C) | Balance to Finish (C-G) | Retainage (If Variable Rate) 10% | Retainage this period
Base Bid General
1 | General Condtions | 100000 | 1 | LS | 100000 | 0 |  | 50000 | 0 | 50000 | 50% | 50000 |  | 5000
2 | Mobilization | 40000 | 1 | LS | 40000 | 0 |  | 20000 | 0 | 20000 | 50% | 20000 |  | 2000
3 | De-Mobilization | 30000 | 1 | LS | 30000 | 0 |  |  | 0 | 0 | 0% | 30000 |  | 0
4 | Overhead Concrete Slab Repairs | 140 | 50 | SF | 7000 | 0 |  |  | 0 | 0 | 0% |  |  | 0
5 | Top of Slab Concrete Repairs | 125 | 30 | SF | 3750 | 0 |  |  | 0 | 0 | 0% |  |  | 0
6 | Edge of Concrete Slab Repairs | 135 | 500 | LF | 67500 | 0 |  |  | 0 | 0 | 0% |  |  | 0
7 | Wall Repairs (Vertical Repairs) | 100 | 50 | SF | 5000 | 0 |  |  | 0 | 0 | 0% | 5000 |  | 0
8 | Partial Concrete Column Repairs | 425 | 40 | CF | 17000 | 0 |  |  | 0 | 0 | 0% | 17000 |  | 0
9 | Epoxy Injection for Crack Repairs | 75 | 100 | LF | 7500 | 0 |  |  | 0 | 0 | 0% | 7500 |  | 0
10 | Crack Repair by Gravity Feed | 48 | 200 | LF | 9600 | 0 |  |  | 0 | 0 | 0% | 9600 |  | 0
11 | Stucco Repair | 30 | 2150 | SF | 64500 | 0 |  |  | 0 | 0 | 0% | 64500 |  | 0
12 | Stucco Crack Repair | 22 | 500 | LF | 11000 | 0 |  |  | 0 | 0 | 0% |  |  | 0
13 | Shutter Removal, Storage, & reinstallation | 115 | 1 | LF | 115 | 0 |  |  | 0 | 0 | 0% | 115 |  | 0
14 | Shutter Removal and Disposal | 50 | 1 | LF | 50 | 0 |  |  | 0 | 0 | 0% | 50 |  | 0
15 | Tile Removal & Disposal on the Balconies | 6.5 | 11250 | SF | 73125 | 0 |  |  | 0 | 0 | 0% | 73125 |  | 0
16 | Removal of Balcony enclosures | 45 | 2700 | LF | 121500 | 0 |  |  | 0 | 0 | 0% | 121500 |  | 0
17 | Replacement of Balcony Englosures (Glass) | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  | 0 |  | 0
18 | Replacement of Balcony Englosures (Standard) | 425000 | 1 | LS | 425000 | 0 |  |  | 0 | 148750 | 35% | 276250 |  | 0
19 | Waterproofing Replacement of the Balconies | 22 | 11250 | SF | 247500 | 0 |  |  | 0 | 0 | 0% | 247500 |  | 0
20 | Waterproofing of Pool Deck | 12 | 12000 | SF | 144000 | 0 |  |  | 0 | 0 | 0% | 144000 |  | 0
21 | Waterproofing of Planters | 19995 | 1 | LS | 19995 | 0 |  |  | 0 | 0 | 0% | 19995 |  | 0
22 | Expansion Joint repairs at Pool Deck | 250 | 230 | LF | 57500 | 0 |  |  |  | 0 | 0% | 57500 |  | 0
23 | Expansion Joint bldg to Pool Deck Slab | 75 | 130 | LF | 9750 | 0 |  |  |  | 0 | 0% | 9750 |  | 0
24 | Paint Preparation | 26550 | 1 | LS | 26550 | 0 |  |  |  | 0 | 0% | 26550 |  | 0
25 | Tower Paint Application | 80442 | 1 | LS | 80442 | 0 |  |  |  | 0 | 0% | 80442 |  | 0
26 | Permit Fees | 1 | 40114 | LS | 40114 | 40114 |  |  |  | 0 | 0% | 40114 |  | 0
| Permit Fees overages |  |  |  | 0 | 8785.21 |  |  |  | 0 |  |  |  | 0
27 | Payment and performance Bond |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0
28 | Additional/Alternate Estimate Allowances |  |  |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0
29 | Replacement of SGD (Dust wall) | 995 |  | LF | 0 | 0 |  |  | 0 | 148750 |  | -148750 |  | 0
Totals: |  |  |  |  | 1608491 | 48899.21 |  | 70000 | 0 | 367500 | 20% | 1151741 | 0 | 7000
31 | Partial Concrete top of Slab Repairs | 125 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
32 | Edge of slab repairs | 135 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
33 | Overhead slab repair | 135 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
34 | Vertical/wall repiar | 100 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
35 | Partial Concrete Beam repair | 425 |  | CF | 0 | 0 |  |  |  | 0 |  |  |  | 0
36 | Partial Concrete Column Repair | 400 |  | CF | 0 | 0 |  |  |  | 0 |  |  |  | 0
37 | Full Depth Slab Repair | 140 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
38 | Concrete crack repair epoxy inject | 75 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
39 | Concrete crack repair Gravity Feed | 48 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
40 | Stucco repair | 30 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
41 | Stucco crack repair | 22 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
42 | painiting repaired area | 5 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
43 | Waterproofing installation on the balcony | 22 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
44 | Tile removal at balconies | 7.5 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
45 | Hourly Labor Rate | 85 |  | HR | 0 | 0 |  |  |  | 0 |  |  |  | 0
46 | Roof Repairs - Time/Labor | 85 |  | HR | 0 | 0 |  |  |  | 60690 |  |  |  | 0
47 | Material Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 0 |  |  |  | 0
48 | Roof Repairs - Material Cost | 4086.7 |  | LS | 0 | 0 |  |  |  | 4086.7 |  |  |  | 0
49 | Roof Repairs - Material Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 408.67 |  |  |  | 0
50 | Subcontractor Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 0 |  |  |  | 0
51 | Equipment Rental Cost Plus | 10% |  | PERC |  | 0 |  |  |  | 0 |  |  |  | 0
52 | Equipment of Balcony Enclosure (glass) | 300 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
53 | Rebar (per contract if needed) | 8.5 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
0 | [13 empty] | 0
Change order total |  | Line item #28 |  |  | 0
Totals: |  |  |  |  | 1608491 | 0 |  | 70000 | 0 | 432685.37 |  | 1151741 | 0 | 7000
Current Payment Due | [8 empty] | 63000 |  |  |  |  | E-M

## Pay App #6
A | B |  |  |  | C | D |  | E | F | G |  | H | I | i
Work Completed
Item No. | Description of Work | unit price | Estimated quantity | Unit | Scheduled Value | From Previous Application (D+E) | Quantity This Period | This Period | Materials Presently Stored (No In D or E) | Total Completed and Stored To Date (D+E+F) | % (G/C) | Balance to Finish (C-G) | Retainage (If Variable Rate) 10% | Retainage this period
Base Bid General
1 | General Condtions | 100000 | 1 | LS | 100000 | 50000 |  |  | 0 | 50000 | 50% | 50000 |  | 0
2 | Mobilization | 40000 | 1 | LS | 40000 | 20000 |  |  | 0 | 20000 | 50% | 20000 |  | 0
3 | De-Mobilization | 30000 | 1 | LS | 30000 | 0 |  |  | 0 | 0 | 0% | 30000 |  | 0
4 | Overhead Concrete Slab Repairs | 140 | 50 | SF | 7000 | 0 |  |  | 0 | 0 | 0% |  |  | 0
5 | Top of Slab Concrete Repairs | 125 | 30 | SF | 3750 | 0 |  |  | 0 | 0 | 0% |  |  | 0
6 | Edge of Concrete Slab Repairs | 135 | 500 | LF | 67500 | 0 |  |  | 0 | 0 | 0% |  |  | 0
7 | Wall Repairs (Vertical Repairs) | 100 | 50 | SF | 5000 | 0 |  |  | 0 | 0 | 0% | 5000 |  | 0
8 | Partial Concrete Column Repairs | 425 | 40 | CF | 17000 | 0 |  |  | 0 | 0 | 0% | 17000 |  | 0
9 | Epoxy Injection for Crack Repairs | 75 | 100 | LF | 7500 | 0 |  |  | 0 | 0 | 0% | 7500 |  | 0
10 | Crack Repair by Gravity Feed | 48 | 200 | LF | 9600 | 0 |  |  | 0 | 0 | 0% | 9600 |  | 0
11 | Stucco Repair | 30 | 2150 | SF | 64500 | 0 |  |  | 0 | 0 | 0% | 64500 |  | 0
12 | Stucco Crack Repair | 22 | 500 | LF | 11000 | 0 |  |  | 0 | 0 | 0% |  |  | 0
13 | Shutter Removal, Storage, & reinstallation | 115 | 1 | LF | 115 | 0 |  |  | 0 | 0 | 0% | 115 |  | 0
14 | Shutter Removal and Disposal | 50 | 1 | LF | 50 | 0 |  |  | 0 | 0 | 0% | 50 |  | 0
15 | Tile Removal & Disposal on the Balconies | 6.5 | 11250 | SF | 73125 | 0 |  |  | 0 | 0 | 0% | 73125 |  | 0
16 | Removal of Balcony enclosures | 45 | 2700 | LF | 121500 | 0 |  |  | 0 | 0 | 0% | 121500 |  | 0
17 | Replacement of Balcony Englosures (Glass) | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  | 0 |  | 0
18 | Replacement of Balcony Englosures (Standard) | 425000 | 1 | LS | 425000 | 0 |  |  | 0 | 148750 | 35% | 276250 |  | 0
19 | Waterproofing Replacement of the Balconies | 22 | 11250 | SF | 247500 | 0 |  |  | 0 | 0 | 0% | 247500 |  | 0
20 | Waterproofing of Pool Deck | 12 | 12000 | SF | 144000 | 0 |  |  | 0 | 0 | 0% | 144000 |  | 0
21 | Waterproofing of Planters | 19995 | 1 | LS | 19995 | 0 |  |  | 0 | 0 | 0% | 19995 |  | 0
22 | Expansion Joint repairs at Pool Deck | 250 | 230 | LF | 57500 | 0 |  |  |  | 0 | 0% | 57500 |  | 0
23 | Expansion Joint bldg to Pool Deck Slab | 75 | 130 | LF | 9750 | 0 |  |  |  | 0 | 0% | 9750 |  | 0
24 | Paint Preparation | 26550 | 1 | LS | 26550 | 0 |  |  |  | 0 | 0% | 26550 |  | 0
25 | Tower Paint Application | 80442 | 1 | LS | 80442 | 0 |  |  |  | 0 | 0% | 80442 |  | 0
26 | Permit Fees | 1 | 40114 | LS | 40114 | 0 |  |  |  | 40114 | 100% | 0 |  | 0
| Permit Fees overages |  |  |  | 8785.21 | 0 |  |  |  | 8785.21 |  |  |  | 0
27 | Payment and performance Bond |  |  |  |  | 0 |  |  |  | 0 |  | 8785.21 |  | 0
28 | Additional/Alternate Estimate Allowances |  |  |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0
29 | Replacement of SGD (Dust wall) | 995 |  | LF | 0 | 0 |  |  | 0 |  |  | 0 |  | 0
Totals: |  |  |  |  | 1617276.21 | 70000 |  | 0 | 0 | 267649.21 | 20% | 1269162.21 | 0 | 0
31 | Partial Concrete top of Slab Repairs | 125 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
32 | Edge of slab repairs | 135 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
33 | Overhead slab repair | 135 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
34 | Vertical/wall repiar | 100 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
35 | Partial Concrete Beam repair | 425 |  | CF | 0 | 0 |  |  |  | 0 |  |  |  | 0
36 | Partial Concrete Column Repair | 400 |  | CF | 0 | 0 |  |  |  | 0 |  |  |  | 0
37 | Full Depth Slab Repair | 140 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
38 | Concrete crack repair epoxy inject | 75 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
39 | Concrete crack repair Gravity Feed | 48 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
40 | Stucco repair | 30 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
41 | Stucco crack repair | 22 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
42 | painiting repaired area | 5 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
43 | Waterproofing installation on the balcony | 22 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
44 | Tile removal at balconies | 7.5 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
45 | Hourly Labor Rate | 85 |  | HR | 0 | 0 |  |  |  | 0 |  |  |  | 0
46 | Roof Repairs - Time/Labor | 85 |  | HR | 0 | 0 |  |  |  | 60690 |  |  |  | 0
47 | Material Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 0 |  |  |  | 0
48 | Roof Repairs - Material Cost | 4086.7 |  | LS | 0 | 0 |  |  |  | 4086.7 |  |  |  | 0
49 | Roof Repairs - Material Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 408.67 |  |  |  | 0
50 | Subcontractor Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 0 |  |  |  | 0
51 | Equipment Rental Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 0 |  |  |  | 0
52 | Equipment of Balcony Enclosure (glass) | 300 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
53 | Rebar (per contract if needed) | 8.5 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
Totals: |  |  |  |  | 1666175.42 | 70000 |  | 0 | 0 | 65185.37 | 20% | 1277947.42 | 0 | 0
Change Orders | [13 empty] | 0
56 | CO#1 - 3 line rail | NA | NA | NA | 0 | 0 |  |  |  | 0 |  |  |  | 0
57 | CO#2 - Remove Stone Wall Section - Center | 40 | 2300 | SF | 92000 | 0 | 2300 | 92000 |  | 92000 |  |  |  | 9200
58 | CO#2 - Remove Stone/Brick - Bottom | 40 | 1863 | SF | 74520 | 0 | 0 | 0 |  | 0 |  |  |  | 0
59 | CO#2 - Additional Mobilization | 16500 | 1 | LS | 16500 | 0 | 1 | 16500 |  | 16500 |  |  |  | 1650
60 | CO#3 - Inspection of shutters for units | 300 | 62 | EA | 18600 | 0 | 62 | 18600 |  | 18600 |  |  |  | 1860
61 | CO#3 - Removal of Shutter Track & Patch |  |  |  |  | 0 | 0 | 0 |  | 0
62 | CO#3- Window Sill Repairs | 375 | 50 | CF | 18750 | 0 | 0 | 0 |  | 0
63 | CO#4- Beam Repairs | 425 | 50 | CF | 21250 | 0 | 0 | 0 |  | 0
64 | CO#5- Full depth Repairs | 150 | 500 | SF | 75000 | 0 | 0 | 0 |  | 0
65 | CO#6- Embedded Metal | 35 | 48 | EA | 1680 | 0 | 0 | 0 |  | 0
Change order total |  |  |  |  | 318300 | 0 |  | 127100 | 0 | 127100 |  |  |  | 12710
Totals: |  |  |  |  | 1984475.42 |  |  | 127100 | 0 | 459934.58 | 0.2 | 1277947.42 | 0 | 12710
Current Payment Due | [8 empty] | 114390 |  |  |  |  | E-M

## Pay App #7
A | B |  |  |  | C | D |  | E | F | G |  | H | I | i
Work Completed
Item No. | Description of Work | unit price | Estimated quantity | Unit | Scheduled Value | From Previous Application (D+E) | Quantity This Period | This Period | Materials Presently Stored (No In D or E) | Total Completed and Stored To Date (D+E+F) | % (G/C) | Balance to Finish (C-G) | Retainage (If Variable Rate) 10% | Retainage this period
Base Bid General
1 | General Condtions | 100000 | 1 | LS | 100000 | 0 |  | 0 | 0 | 50000 | 50% | 50000 |  | 0
2 | Mobilization | 40000 | 1 | LS | 40000 | 0 |  | 0 | 0 | 20000 | 50% | 20000 |  | 0
3 | De-Mobilization | 30000 | 1 | LS | 30000 | 0 |  | 0 | 0 | 0 | 0% | 30000 |  | 0
4 | Overhead Concrete Slab Repairs | 140 | 50 | SF | 7000 | 0 |  | 0 | 0 | 0 | 0% | 7000 |  | 0
5 | Top of Slab Concrete Repairs | 125 | 30 | SF | 3750 | 0 |  | 0 | 0 | 0 | 0% | 3750 |  | 0
6 | Edge of Concrete Slab Repairs | 135 | 500 | LF | 67500 | 0 |  | 0 | 0 | 0 | 0% | 67500 |  | 0
7 | Wall Repairs (Vertical Repairs) | 100 | 50 | SF | 5000 | 0 |  | 0 | 0 | 0 | 0% | 5000 |  | 0
8 | Partial Concrete Column Repairs | 425 | 40 | CF | 17000 | 0 |  | 0 | 0 | 0 | 0% | 17000 |  | 0
9 | Epoxy Injection for Crack Repairs | 75 | 100 | LF | 7500 | 0 |  | 0 | 0 | 0 | 0% | 7500 |  | 0
10 | Crack Repair by Gravity Feed | 48 | 200 | LF | 9600 | 0 |  | 0 | 0 | 0 | 0% | 9600 |  | 0
11 | Stucco Repair | 30 | 2150 | SF | 64500 | 0 | 105.15 | 3154.5 | 0 | 3154.5 | 4.891% | 61345.5 |  | 315.45
12 | Stucco Crack Repair | 22 | 500 | LF | 11000 | 0 | 0 | 0 | 0 | 0 | 0% | 11000 |  | 0
13 | Shutter Removal | 50 | 1 | LF | 50 | 0 | 491.33 | 24566.5 | 0 | 24566.5 |  |  |  | 2456.65
14 | Shutter Reinstallation | 65 | 1 | LF | 65 | 0 | 0 | 0 | 0 | 0 | 0% | 65 |  | 0
15 | Tile Removal & Disposal on the Balconies | 6.5 | 11250 | SF | 73125 | 0 | 2332.94 | 15164.11 | 0 | 15164.11 | 20.74% | 57960.89 |  | 1516.411
16 | Removal of Balcony enclosures | 45 | 2700 | LF | 121500 | 0 | 432.5 | 19462.5 | 0 | 19462.5 | 16.02% | 102037.5 |  | 1946.25
17 | Replacement of Balcony Englosures (Glass) | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0
18 | Replacement of Balcony Englosures (Standard) | 425000 | 1 | LS | 425000 | 0 |  | 0 | 0 | 148750 | 35% | 276250 |  | 0
19 | Waterproofing Replacement of the Balconies | 22 | 11250 | SF | 247500 | 0 |  | 0 | 0 | 0 | 0% | 247500 |  | 0
20 | Waterproofing of Pool Deck | 12 | 12000 | SF | 144000 | 0 |  | 0 | 0 | 0 | 0% | 144000 |  | 0
21 | Waterproofing of Planters | 19995 | 1 | LS | 19995 | 0 |  | 0 | 0 | 0 | 0% | 19995 |  | 0
22 | Expansion Joint repairs at Pool Deck | 250 | 230 | LF | 57500 | 0 |  | 0 |  | 0 | 0% | 57500 |  | 0
23 | Expansion Joint bldg to Pool Deck Slab | 75 | 130 | LF | 9750 | 0 |  | 0 |  | 0 | 0% | 9750 |  | 0
24 | Paint Preparation | 26550 | 1 | LS | 26550 | 0 |  | 0 |  | 0 | 0% | 26550 |  | 0
25 | Tower Paint Application | 80442 | 1 | LS | 80442 | 0 |  | 0 |  | 0 | 0% | 80442 |  | 0
26 | Permit Fees | 1 | 40114 | LS | 40114 | 0 |  | 0 |  | 40114 | 100% | 0 |  | 0
| Permit Fees overages |  |  |  | 8785.21 | 0 |  | 0 |  | 8785.21 |  | 0 |  | 0
27 | Payment and performance Bond |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | Additional/Alternate Estimate Allowances |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
29 | Replacement of SGD (Dust wall) | 995 |  | LF | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0
Totals: |  |  |  |  | 1617226.21 | 0 |  | 62347.61 | 0 | 329996.82 | 20% | 1311745.89 | 0 | 6234.761
31 | Partial Concrete top of Slab Repairs | 125 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
32 | Edge of slab repairs | 135 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
33 | Overhead slab repair | 135 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
34 | Vertical/wall repiar | 100 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
35 | Partial Concrete Beam repair | 425 |  | CF | 0 | 0 |  |  |  | 0 |  |  |  | 0
36 | Partial Concrete Column Repair | 400 |  | CF | 0 | 0 |  |  |  | 0 |  |  |  | 0
37 | Full Depth Slab Repair | 140 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
38 | Concrete crack repair epoxy inject | 75 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
39 | Concrete crack repair Gravity Feed | 48 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
40 | Stucco repair | 30 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
41 | Stucco crack repair | 22 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
42 | painiting repaired area | 5 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
43 | Waterproofing installation on the balcony | 22 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
44 | Tile removal at balconies | 7.5 |  | SF | 0 | 0 |  |  |  | 0 |  |  |  | 0
45 | Hourly Labor Rate | 85 |  | HR | 0 | 0 |  |  |  | 0 |  |  |  | 0
46 | Roof Repairs - Time/Labor | 85 |  | HR | 0 | 0 |  |  |  | 60690 |  |  |  | 0
47 | Material Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 0 |  |  |  | 0
48 | Roof Repairs - Material Cost | 4086.7 |  | LS | 0 | 0 |  |  |  | 4086.7 |  |  |  | 0
49 | Roof Repairs - Material Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 408.67 |  |  |  | 0
50 | Subcontractor Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 0 |  |  |  | 0
51 | Equipment Rental Cost Plus | 10% |  | PERC | 0 | 0 |  |  |  | 0 |  |  |  | 0
52 | Equipment of Balcony Enclosure (glass) | 300 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
53 | Rebar (per contract if needed) | 8.5 |  | LF | 0 | 0 |  |  |  | 0 |  |  |  | 0
Totals: |  |  |  |  | 1666125.42 | 0 |  | 0 | 0 | 65185.37 | 0 | 0 | 0 | 0
Change Orders | [13 empty] | 0
56 | CO#1 - 3 line rail | NA | NA | NA | 0 |  |  |  |  | 0 |  | 0 |  | 0
57 | CO#2 - Remove Stone Wall Section - Center | 40 | 2300 | SF | 92000 | 92000 |  | 0 |  | 92000 |  | 0 |  | 0
58 | CO#2 - Remove Stone/Brick - Bottom | 40 | 1863 | SF | 74520 | 0 |  | 0 |  | 0 |  | 74520 |  | 0
59 | CO#2 - Additional Mobilization | 16500 | 1 | LS | 16500 | 16500 |  | 0 |  | 16500 |  | 0 |  | 0
60 | CO#3 - Inspection of shutters for units | 300 | 62 | EA | 18600 | 18600 |  | 0 |  | 18600 |  | 0 |  | 0
61 | CO#3 - Removal of Shutter Track & Patch |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
62 | CO#3- Window Sill Repairs | 375 | 50 | CF | 18750 | 0 | 2.16 | 810 |  | 810 |  | 17940 |  | 81
63 | CO#4- Beam Repairs | 425 | 50 | CF | 21250 | 0 | 6 | 2550 |  | 2550 |  | 18700 |  | 255
64 | CO#5- Full depth Repairs | 150 | 500 | SF | 75000 | 0 | 0 | 0 |  | 0 |  | 75000 |  | 0
65 | CO#6- Embedded Metal | 35 | 48 | EA | 1680 | 0 | 2 | 70 |  | 70 |  | 1610 |  | 7
Change order total |  |  |  |  | 318300 | 127100 |  | 3430 | 0 | 130530 |  | 187770 |  | 343 | TOTAL RETAINAGE TO DATE:
Totals: |  |  |  |  | 1984425.42 |  |  | 65777.61 | 0 | 525712.19 |  | 1499515.89 | 0 | 6577.761 | 52571.219
Current Payment Due | [8 empty] | 59199.849 |  |  |  |  | E-M
TOTAL REMAINING LEFT:
1552087.109